## Table___Progress_New_model_Mast
ID Progress | Part No | JO No | Date | Activity | Activity Description | PIC Progress | PIC Customer | Process Trial | Mesin | DH | Material Actual trial | Qty Material | Qty Process | Problem | Poto Problem | Corrective Action | Next Action | PIC Corrective Action | Date Corrective Action | PIC Next Action | Date Next Action | Qty Sample | Ket Event | Date Feedback Customer | Feedback Customer | Feedback Customer Link | PIC Feedback Customer | Doc1 | Doc1 link | Doc2 | Doc2 link | Doc3 | Doc3 link | Doc4 | Doc4 link | Doc5 | Doc5 link | Ket Doc1 | Ket Doc2 | Ket Doc3 | Ket Doc4 | Ket Doc5 | Progress Close | Remark Progress
12 |  | 21-BMI01 | 2024-12-20 | Sent Sample | Evaluasi sample by TBJ | Saudi | [6 empty] | 0 | [8 empty] | 0 | N30 | 2024-12-20 | Spring Caracteristic Max, Act 39-41 N | ..\..\..\PROJECT\NEW MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook Clamp\Evaluasi TBINA\Spring Caracteristic - 241220_TBINAクランプ現調化_ばね特性まとめ.xlsx#..\..\..\PROJECT\NEW%20MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook%20Clamp\Evaluasi%20TBINA\Spring%20Caracteristic%20-%20241220_TBINAクランプ現調化_ばね特性まとめ.xlsx# | [16 empty] | FALSE
17 |  | 21-BMI01 | 2025-01-08 | Trial | Trial Evaluasi Spring Caracteristic |  |  |  | NST |  |  |  | 0 | 1. Variasi Parameter : Speed Conveyor (30/45/60) dan Temperatur Quencing (350/360/370 => Spring Caracteristic tetap Out Std 32+/-5 N Act 37 ~ 41 N |  | Continue evaluasi point/proses lain - Material - Proses Forming |  | Saudi |  |  |  | 0 | Follow up evaluasi TBJ |  |  |  |  | Data Spring Caracteristic#http://Data Spring Caracteristic# | ..\..\..\PROJECT\NEW MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook Clamp\Spring Caracteristic HOOK CLAMP - Trial NST 080125.xlsx#..\..\..\PROJECT\NEW%20MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook%20Clamp\Spring%20Caracteristic%20HOOK%20CLAMP%20-%20Trial%20NST%20080125.xlsx# | [13 empty] | FALSE
18 |  | 21-BMI04 |  | Trial | Trial | [7 empty] | 2 | [8 empty] | 0 | Sample pengukuran | [19 empty] | FALSE
19 |  | 21-BMI04 |  | Sent Sample | Sample perbaikan forming, add thickness problem durability pecah | [7 empty] | 0 | [8 empty] | 2 | [20 empty] | FALSE
21 |  | 123.017 | 2025-01-07 | Sent Sample | Sample N30 |  | Danielo, Oman | [5 empty] | 0 |  |  | Check N5 Full dimensi Drawing | Kirim lagi sample n30 | Fery | 2025-01-11 | Saudi | 2025-01-20 | 30 | N30 | 2025-01-07 | Request data N5 Full Drawing, Produk dikembalikan untuk check ulang |  | Danielo | Checksheet N5 Full Dimensi#http://Checksheet N5 Full Dimensi# | \\Desktop-qt8odod\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data N5 Full Drawing Lower Plate 163 x 99 - VMVRIP-BB03900-SB Sample N30.xlsx#\\Desktop-qt8odod\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data N5 Full Drawing Lower Plate 163 x 99 - VMVRIP-BB03900-SB Sample N30.xlsx# | Cp/Cpk N30 | \\Desktop-qt8odod\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Cpk Lower Plate PT Velasto-1ae.xlsx#\\Desktop-qt8odod\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Cpk Lower Plate PT Velasto-1ae.xlsx# | [11 empty] | FALSE
22 |  | 123.018 | 2025-01-07 | Sent Sample | Sample N30 | [7 empty] | 0 |  |  | Check N5 Full dimensi Drawing | Kirim lagi sample n30 | Fery | 2025-01-11 | Lija | 2025-01-20 | 0 | N30 | 2025-01-07 | Request data N5 Full Drawing Part dikembalikan untuk check ulang | [17 empty] | FALSE
24 |  | 21-BMI01 | 2025-01-15 | Trial | Trial Beda Lot Material - Manual Bending |  |  |  | Manual rol |  |  |  | 10 | prioduk tidak stabil, karena dibuat manual, hasil check tidak stabil dan tidak bisa dijadikan acuan data | [7 empty] | 0 | Improvement | [19 empty] | FALSE | Untuk melihat Perbadaan Spring Caracteristic dengan beda lot material (beda supplier juga)
25 |  | 21-BMI01 | 2025-01-15 | Trial | Trial Beda Lot Material proses Forming |  |  |  | F-03 |  | SK85M |  | 30 | Setelah trial Harden di NST 16-1-25 Spring Caracteristik masih Maximal | [8 empty] | Improvement |  |  |  |  | Spring Caracteristic Beda lot material | ..\..\..\PROJECT\NEW MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook Clamp\Spring Caracteristic HOOK CLAMP - Trial Beda Lot Material 160125.xlsx#..\..\..\PROJECT\NEW%20MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook%20Clamp\Spring%20Caracteristic%20HOOK%20CLAMP%20-%20Trial%20Beda%20Lot%20Material%20160125.xlsx# | [13 empty] | FALSE | Trial Spring caracteristic dengan material beda lot dan beda supplier Lot: M-011222 (Lot lama paacking buiru) Hanwa: Qty 10; M-271223 Qty 10; dan lot M-120224 qty 10
26 |  | 124.138 | 2025-01-15 | Sent Sample | Kirim sample material | [6 empty] | 1 | 0 | [8 empty] | 0 | SOC Free |  |  |  |  | Resi#http://Resi# | \\Desktop-qt8odod\project\NEW MODEL\INOVATEK\Others\Resi kirim sample material Inovatek 3 parts.jpeg#\\Desktop-qt8odod\project\NEW MODEL\INOVATEK\Others\Resi kirim sample material Inovatek 3 parts.jpeg# | [13 empty] | FALSE
27 |  | 123.017 | 2025-01-20 | Sent Sample | Re-Send sample N30 + Checksheet N5Full Drawing+CpCpk | [7 empty] | 0 | [8 empty] | 26 | N30 |  | Checksheet QC VIN OK, Info Pak Oman by WAG VIN-BMI 30-1-25 |  |  | Checksheet N5 Full Dimensi | \\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data N5 Full Drawing Lower Plate 163 x 99 - VMVRIP-BB03900-SB Sample N30.xlsx#\\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data N5 Full Drawing Lower Plate 163 x 99 - VMVRIP-BB03900-SB Sample N30.xlsx# | N30 Cp Cpk | \\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data Cp Cpk - LOWER PLATE 163 X 99 - VIN Event N30.xls#\\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Data Cp Cpk - LOWER PLATE 163 X 99 - VIN Event N30.xls# | CS VIN | \\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Result N-30 Metal Lower plate (HN048) CS VIN 210125.pdf#\\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Lower\Result N-30 Metal Lower plate (HN048) CS VIN 210125.pdf# | [9 empty] | FALSE
28 |  | 123.018 | 2025-01-20 | Sent Sample | Re-Send sample N30 + Checksheet N5Full Drawing+CpCpk |  | Daniel, Oman | [5 empty] | 0 | [8 empty] | 30 | N30 |  | Checksheet QC VIN OK, Info Pak Oman by WAG VIN-BMI 30-1-25 |  |  | Checksheet N5 Full Dimensi |  | N30 Cp Cpk |  | CS VIN | \\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Upper\Result N-30 Metal Upper plate (HN048) CS VIN 210125.pdf#\\Qc-system\project\NEW MODEL\Velasto - IKP\HN048\Inspeksi\Upper\Result N-30 Metal Upper plate (HN048) CS VIN 210125.pdf# | [9 empty] | FALSE
31 |  | 123.018 | 2025-01-20 | [9 empty] | 0 | [8 empty] | 0 | [20 empty] | FALSE
32 |  | 123.018 | 2025-01-20 | [9 empty] | 0 | [8 empty] | 0 | [20 empty] | FALSE
33 |  | 21-BMI01 | 2025-01-23 | Trial | Trial Beda Lot Material proses Forming |  |  |  | F-03 |  | SK85M |  | 2300 | [8 empty] | 0 | Improvement | [19 empty] | FALSE | Persiapan untuk next trial Spring caracteristic dengan material beda lot dan beda supplier Lot: M-011222 (Lot lama paacking buiru) Hanwa: Qty 1000; M-271223 Qty 1000; dan lot M-120224 qty 300
34 |  | 124.138 | 2025-01-25 | Trial | Trial Improvement Sobekan |  |  |  | F07 |  | SK85M |  | 0 | Burring Pecah | [7 empty] | 0 | Improvement Feedback Inovatek | [19 empty] | FALSE
35 |  | 124.145 | 2025-01-26 | Trial | Trial improvement Celah | [5 empty] | SK85M |  | 1000 | Tidak Stabil, Setelah 150pcs proses tidak stabil masih setting setting | [7 empty] | 0 | Improvement request Inovatek | [19 empty] | TRUE
36 |  | 124.138 | 2025-01-26 | Trial | Trial Improvement Sobekan | [5 empty] | SK85M |  | 500 | [8 empty] | 0 | Improvement Feedback Inovatek | [19 empty] | FALSE
37 |  | 123.018 | 2025-02-03 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Part Inspection Standard |  | QCPC |  | Quality Check Sheet |  | Standard Packaging | [8 empty] | FALSE | kirim 3 Feb 25, via driver delivery
38 |  | 123.017 | 2025-02-03 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Part Inspection Standard |  | QCPC |  | Quality Check Sheet |  | Packaging Standard | [8 empty] | FALSE | Kirim 3 Februari, via driver delivery
39 |  | 123.016 | 2025-02-03 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval | 2025-02-05 |  |  | P' Oman | Part Inspection Standard |  | QCPC |  | Quality Check Sheet |  | Packaging Standard | [8 empty] | FALSE | Kirim 3 Februari 2025, via driver delivery
41 |  | 124.145 | 2025-01-31 | Trial | Trial Oven (SKS) untuk Warna gelap posphating |  |  |  | Oven SKS |  | SK85M |  | 500 | Setelah Oven sks, warna bakaran masih kurang gelap |  | Kirim ke Eudonia untuk posphating | Trial Harden NST untuk warna lebih gelap | Susi | 2025-02-03 | Yola | 2025-02-03 | 0 | Approval | [19 empty] | FALSE
42 |  | 124.146 | 2025-02-01 | Trial | Trial dimprove dimensi dan untuk warna nickel plating sama sample | [7 empty] | 300 | Dimensi masih problem Point 7 Std 2+-0.1 act 0.08 / o.15 dan point 8 std 8+-0,5 act 14.58 |  | Lanjutkan perbaikan | pararel kirim sample ke NST dan Eudonia untuk trial warna nickel palting | Ali | 2025-02-03 | Yola | 2025-02-05 | 0 | Approval | [19 empty] | FALSE
43 |  | 124.146 | 2025-02-05 | Trial | Kirim sample untuk Trial Harden NST untuk trial warna nickel palting |  |  |  | NST |  | SK85M |  | 300 | [8 empty] | 300 | Approval | [19 empty] | FALSE
44 |  | 124.146 | 2025-02-07 | Trial | Kirim sample ke Eudonia untuk Trial warna nickel plating after HT NST | [7 empty] | 0 | [8 empty] | 300 | Approval | [19 empty] | FALSE | Warna Plating = Sample Inovatek
45 |  | 124.145 | 2025-02-06 | Trial | Trial posphating Eudonia untuk warna sesuai sample dari Lot HT SKS | [5 empty] | SK85M |  | 200 | Warna kurang hitam | [7 empty] | 0 | Approval | [19 empty] | FALSE | Lot proses SKS
46 |  | 21-BMI03 |  | Audit | [8 empty] | 0 | [8 empty] | 0 | [20 empty] | FALSE
47 |  | 123.017 | 2025-02-03 | Sent Sample | Re Sent Sample n30 full Stamping tanpa Hand Grinding | [16 empty] | 30 | N30 |  |  |  |  | QCS | [14 empty] | FALSE
48 |  | 123.016 | 2025-02-10 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Quality Control Plan (QCP) |  | Part Inspection Standard (PIS) |  | Quality Check Sheet (QCS) |  | Process Failure Mode and Effect Analysis (PFMEA) |  | Check Sheet Inspection Jig | [6 empty] | FALSE | 6. PSW Letter, 7. Drawing, 8. Millsheet, 9. SOC Free, 10. Data Cp/Cpk & N5 Cover Plate (Sample Tanggal 23/01/25), dokumen dikirim oleh driver delivery
49 |  | 123.017 | 2025-02-10 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Quality Control Plan (QCP) |  | Part Inspection Standard (PIS) |  | Quality Check Sheet (QCS) |  | Process Failure Mode and Effect Analysis (PFMEA) |  | Check Sheet Inspection Jig | [6 empty] | FALSE | 6. PSW Letter, 7. Drawing, 8. Millsheet, 9. SOC Free, 10. Data Cp/Cpk & N5 Cover Plate (Sample Tanggal 23/01/25), dokumen dikirim oleh driver delivery
50 |  | 123.018 | 2025-02-10 | Send Document | Kirim Dokumen Approval |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Quality Control Plan (QCP) |  | Part Inspection Standard (PIS) |  | Quality Check Sheet (QCS) |  | Process Failure Mode and Effect Analysis (PFMEA) |  | Check Sheet Inspection Jig | [6 empty] | FALSE | 6. PSW Letter, 7. Drawing, 8. Millsheet, 9. SOC Free, 10. Data Cp/Cpk & N5 Cover Plate (Sample Tanggal 23/01/25), dokumen dikirim oleh driver delivery
51 |  | 124.145 | 2025-02-08 | Trial | Trial posphating Eudonia untuk warna sesuai sample dari Lot HT NST | [7 empty] | 300 | Warna Hitam sama dengan Sample Inovatek | [7 empty] | 0 | Approval | [19 empty] | FALSE | Info di WAG Inovatek BMI
52 |  | 124.138 | 2025-02-08 | Trial | Improve Sobekan | [7 empty] | 0 | Sobekan masih kecil, belum sama sample |  | Lanjut repair dan trial |  | Ali Akbar | 2025-02-10 |  |  | 0 | Approval |  |  |  |  | CS Sobekan | \\Qc-system\project\NEW MODEL\INOVATEK\Nut\Inspeksi\Checkseet Nut Inovatek Trial Sobekan.xlsx#\\Qc-system\project\NEW MODEL\INOVATEK\Nut\Inspeksi\Checkseet Nut Inovatek Trial Sobekan.xlsx# | [13 empty] | FALSE
53 |  | 124.145 | 2025-02-11 | Sent Sample | Send sample perbaikan warna posphating dengan add harden supaya warna pospating hitam | [10 empty] | Temp : Repair stock => Celah 1.3 ~ 1.5 Kirim ulang sample | Setting ulang proses Forming | Saudi | 2025-02-19 | Triyuni |  | 20 | Approval |  | Celah Maksimal dibandingkan sample Inovatek Actual celah : 1.65 ~ 1.7 | [17 empty] | FALSE
54 |  | 124.146 | 2025-02-11 | Sent Sample | Send sample improve warna Nickel Plating refer to sample | [7 empty] | 0 |  |  | Temp: Repair stock untuk kirim sample Jarak 9,5 Actual 10,14 direpair menjadi 9,5 | Koreksi proses Forming | Fery | 2025-02-19 |  |  | 20 | Approval |  | Gap besar => Fitting test keras | [17 empty] | FALSE
55 |  | 21-BMI01 | 2025-02-14 | Trial | Trial Heat Treatment di NST. HV menyamakan sample TBINA, untuk dikirim ke TBINA , TBJ | [7 empty] | 400 | [8 empty] | 0 | Improve Spring Caracteristic | [19 empty] | FALSE | Trial 2 Lot. Sudah kirim ke BMI …..
56 |  | 21-BMI01 | 2025-02-19 | Trial | Trial Plating di SSP setelah HT HV menyamakan sample TBINA, untuk dikirim ke TBINA , TBJ | [7 empty] | 400 | [8 empty] | 0 | Improve Spring Caracteristic | [19 empty] | FALSE | Dari SSP sudah kirim BMI 22-Feb-25
58 |  | 21-BMI01 | 2025-02-26 | Sent Sample | Sample Perbaikan Spring Characteristics (M23-250225/1) |  | Pak Taufik | [5 empty] | 0 | [8 empty] | 150 | Improvement |  |  |  |  | QCS Hook Clamp Perbaikan Spring Characteristics 260225 | ..\..\..\PROJECT\NEW MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook Clamp\QCS Hook Clamp (Sample Perbaikan Spring Caracteristic) - 260225.pdf#..\..\..\PROJECT\NEW%20MODEL\TBINA\Lokalisasi-1\Inspeksi\Hook%20Clamp\QCS%20Hook%20Clamp%20(Sample%20Perbaikan%20Spring%20Caracteristic)%20-%20260225.pdf# | [13 empty] | FALSE
59 |  | 21-BMI04 | 2025-02-26 | Sent Sample | Sample | [7 empty] | 0 | [8 empty] | 10 |  | 2025-03-08 | Analisa/pelajari cara ukur flatness |  |  | QCS As Ting Tong - Sent Sample 260225 | ..\..\..\PROJECT\NEW MODEL\FTR\As Thingtonk\QCS As Ting Tong - Sent Sample 260225.pdf#..\..\..\PROJECT\NEW%20MODEL\FTR\As%20Thingtonk\QCS%20As%20Ting%20Tong%20-%20Sent%20Sample%20260225.pdf# | [13 empty] | FALSE
60 |  | 124.138 | 2025-03-06 | Sent Sample | Sample Proses Geomet Silver |  | Pak Tanjung | [5 empty] | 0 | [8 empty] | 5 | [20 empty] | FALSE | Sent via Gojek
61 |  | 124.145 | 2025-03-03 | Trial | Trial Kestabilan Celah |  |  |  | F02 |  | SK85M |  | 500 | [8 empty] | 0 | Improvement |  |  |  |  | Cp Cpk | ..\..\..\PROJECT\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk N80 NUT SPRING - Cek Celah.xls#..\..\..\PROJECT\NEW%20MODEL\INOVATEK\Nut,%20Spring\Inspection\Cpk%20N80%20NUT%20SPRING%20-%20Cek%20Celah.xls# | QCS | [12 empty] | FALSE | Celah sudah OK (1,3) - Cp : 5,73 & Cpk : 0,52
62 |  | 124.138 | 2025-02-22 | Trial | Trial Perbaikan (Geser Dies) |  |  |  | F07 |  | SK85M |  | 0 | Sobekan taring kurang panjang | [7 empty] | 0 | Improvement | [19 empty] | FALSE
63 |  | 124.138 | 2025-02-27 | Trial | [6 empty] | SK85M |  | 0 | Celah max | [7 empty] | 0 | Improvement | [19 empty] | FALSE
64 |  | 21-BMI04 | 2025-03-05 | Trial | Trial (material baru) | [7 empty] | 0 | [8 empty] | 0 | [5 empty] | QCS As Ting Tong - Trial 050325 | ..\..\..\PROJECT\NEW MODEL\FTR\As Thingtonk\QCS As Ting Tong - Trial 050325.pdf#..\..\..\PROJECT\NEW%20MODEL\FTR\As%20Thingtonk\QCS%20As%20Ting%20Tong%20-%20Trial%20050325.pdf# | [13 empty] | FALSE | Cek flatness menggunakan 2 metode (Height Gauge & Hexagon)
65 |  | 124.146 | 2025-03-06 | Trial | Trial perbaikan kerapatan gap | [7 empty] | 0 | Poin 3 belum sesuai spesifikasi, Punch bending patah | [7 empty] | 0 | [5 empty] | QCS Trial 060325 | ..\..\..\PROJECT\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\QCS Spring Console - Trial 080325.pdf#..\..\..\PROJECT\NEW%20MODEL\INOVATEK\SPRING,%20CONSOLE%20DOOR%20STOPPER\Inspeksi\QCS%20Spring%20Console%20-%20Trial%20080325.pdf# | [13 empty] | FALSE
66 |  | 124.146 | 2025-03-08 | Trial | Trial Perbaikan jarak point 6 jarak 9.6=> 9.5, Untuk Trial Heat Treatment HV Minim (HV440-460) | [7 empty] | 0 | Camp 12 gompal |  | Wire cut ulang |  | Ali | 2025-03-08 |  |  | 0 | [5 empty] | Quality Check Sheet | ..\..\..\PROJECT\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\QCS Spring Console - Trial 080325.pdf#..\..\..\PROJECT\NEW%20MODEL\INOVATEK\SPRING,%20CONSOLE%20DOOR%20STOPPER\Inspeksi\QCS%20Spring%20Console%20-%20Trial%20080325.pdf# | [13 empty] | FALSE
67 |  | 21-BMI04 | 2025-03-10 | Sent Sample | Sample Flatness OK | [7 empty] | 0 | [8 empty] | 2 | Improvement | 2025-04-10 | Untuk mengecek kekuatan saat di baut. Improve nya dari analisa FTR akan: -Merubah tebal material menjadi lebih tebal. (act. T. 6.mm) -Penambahan pelicin matrial di proses swaging. Harapan FTR menunggu masukan dari BMI untuk prosesnya, agar bisa mendekati hasil pengecekan dari Part BMI dan Part Jepang. | \\Qc-system\project\NEW MODEL\FTR\As Thingtonk\As Tingtong Feedback Cust. Sent Sample 100325.pdf#\\Qc-system\project\NEW MODEL\FTR\As Thingtonk\As Tingtong Feedback Cust. Sent Sample 100325.pdf# | Pak Cahyo | QCS As Ting Tong | ..\..\..\PROJECT\NEW MODEL\FTR\As Thingtonk\QCS As Ting Tong - Sent Sample 100325.pdf#..\..\..\PROJECT\NEW%20MODEL\FTR\As%20Thingtonk\QCS%20As%20Ting%20Tong%20-%20Sent%20Sample%20100325.pdf# | [13 empty] | FALSE | Flatness OK
68 |  | 124.146 | 2025-03-10 | Trial | Trial Perbaikan point 3 jarak 9.6 => 9.3 dan 9.5, Untuk Trial Heat Treatment HV Minim (HV440-460) |  |  |  | F01 |  | SK85M |  | 463 |  |  |  | kirim sample HT ke NST dan ST ke Eudonia |  |  | Ersa | 2025-03-12 |  | Improvement |  |  |  |  | Cp Cpk 9.3 | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sebelum Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sebelum Harden).xls# | Cp Cpk 9.5 | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sebelum Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sebelum Harden).xls# | Cp Cpk 9.3 Sebelum Harden | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sebelum Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sebelum Harden).xls# | Cp Cpk 9.5 Sebelum Harden | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sebelum Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sebelum Harden).xls# | [7 empty] | FALSE | Tinggi 9.3mm @141pcs (LOT A) & tinggi 9.5mm @322pcs (LOT B)
69 |  | 123.016 | 2025-03-11 | Send Document | Kirim Dokumen Packaging Standard Rev.01 |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Packaging Standard | ..\..\..\PROJECT\NEW MODEL\Velasto - IKP\HN048\PQCS\REV DOC VELASTO Cover\Packaging Standard - Cover Plate - 01HN-2003-13 Rev.01.pdf#..\..\..\PROJECT\NEW%20MODEL\Velasto%20-%20IKP\HN048\PQCS\REV%20DOC%20VELASTO%20Cover\Packaging%20Standard%20-%20Cover%20Plate%20-%2001HN-2003-13%20Rev.01.pdf# | [13 empty] | FALSE | Kirim 11 Maret 2025, via driver delivery
70 |  | 123.017 | 2025-03-11 | Send Document | Kirim Dokumen Packaging Standard Rev.01 |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Packaging Standard Rev.01 | ..\..\..\PROJECT\NEW MODEL\Velasto - IKP\HN048\PQCS\REV DOC VELASTO Lower\Packaging Standard Lower Plate Rev.01.pdf#..\..\..\PROJECT\NEW%20MODEL\Velasto%20-%20IKP\HN048\PQCS\REV%20DOC%20VELASTO%20Lower\Packaging%20Standard%20Lower%20Plate%20Rev.01.pdf# | [13 empty] | FALSE | Kirim 11 Maret 2025, via driver delivery
71 |  | 123.018 | 2025-03-11 |  | Kirim Dokumen Packaging Standard Rev.01 |  | P' Oman, P' Daniel | [5 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Packaging Standard Rev.01 | ..\..\..\PROJECT\NEW MODEL\Velasto - IKP\HN048\PQCS\REV DOC VELASTO Upper\Packaging Standard Upper Plate 132 x 86 Rev.01.pdf#..\..\..\PROJECT\NEW%20MODEL\Velasto%20-%20IKP\HN048\PQCS\REV%20DOC%20VELASTO%20Upper\Packaging%20Standard%20Upper%20Plate%20132%20x%2086%20Rev.01.pdf# | [13 empty] | FALSE
72 |  | 123.018 | 2025-03-11 | Send Document | Kirim Dokumen Packaging Standard Rev. 01 | [7 empty] | 0 | [8 empty] | 0 | Approval |  |  |  |  | Packaging Standard Rev. 01 | ..\..\..\PROJECT\NEW MODEL\Velasto - IKP\HN048\PQCS\REV DOC VELASTO Upper\Packaging Standard Upper Plate 132 x 86 Rev.01.pdf#..\..\..\PROJECT\NEW%20MODEL\Velasto%20-%20IKP\HN048\PQCS\REV%20DOC%20VELASTO%20Upper\Packaging%20Standard%20Upper%20Plate%20132%20x%2086%20Rev.01.pdf# | [13 empty] | FALSE | Kirim 11 Maret 2025, via driver delivery
73 |  | 124.138 | 2025-03-13 | Trial | Trial untuk hardening |  |  |  | F07 |  | SPS60 |  | 500 | Part tidak flate area sisi burring |  |  | Kirim sample 500pcs ke MEIDO |  |  | Ersa | 2025-03-15 | 0 | Improvement |  |  |  |  | Quality Check Sheet | [14 empty] | FALSE
74 |  | 21-BMI05 | 2025-03-17 | Trial | Stamping Blank |  | Pak Rudy |  | P02 | 2931 |  |  | 234 | -Material tidak masuk stopper di OP 10 -Lebar material variasi dari ujung hingga ke tengah material |  | -Adjuster Stopper di OP 10 -Konfirmasi ke Pandawa |  |  | 2025-03-17 |  |  | 0 | HVPT |  |  |  |  | Check Sheet | \\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Reinf., 1 - Trial HVPT 170325.pdf#\\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Reinf., 1 - Trial HVPT 170325.pdf# | Trial Report | [12 empty] | FALSE | C/T = 02.03 m/sheet = 4 detik/pcs
75 |  | 21-BMI05 | 2025-03-17 | Trial | Stamping Bending |  | Pak Rudy |  | P01 | 2930 |  |  | 234 | [8 empty] | 0 | HVPT |  |  |  |  | Check Sheet | \\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Reinf., 1 - Trial HVPT 170325.pdf#\\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Reinf., 1 - Trial HVPT 170325.pdf# | Trial Report | [12 empty] | FALSE | C/T = 45 detik/10 pcs PPM = 12 SPH = 720 (Improve lagi)
76 |  | 124.114 | 2025-03-17 | Trial | Stamping Blank - Piercing |  | Pak Rudy |  | P01 | 3230 |  |  | 208 | Material tidak masuk stopper Act : 4.0 x 65 x 1228 BQ = 26 Std PSL : 4.0 x 63 x 1219 BQ = 24 |  | -Lepas stopper sisi kanan (Temporary) -Std PSL : 4.0 x 63 x 1228 BQ = 26 (Self Purchase) |  | -Pak Andi -Bu Lija | 2025-03-17 |  |  | 0 | HVPT |  |  |  |  | Check Sheet | \\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Brkt Switch - Trial HVPT 170325.pdf#\\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Brkt Switch - Trial HVPT 170325.pdf# | Trial Report | [12 empty] | FALSE | C/T = 02.44 m/sheet = 6 detik/pcs
77 |  | 124.114 | 2025-03-17 | Trial | Tapping |  |  |  | T01 |  |  |  | 0 | Scrap masuk ke dalam ulir dan burry |  | Pergantian mata bor sisi kanan dan semprot angin setiap 1 cycle proses |  | Pak Andi | 2025-03-17 |  |  | 0 | HVPT |  |  |  |  | Check Sheet | \\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Brkt Switch - Trial HVPT 170325.pdf#\\Qc-system\project\NEW MODEL\MES\BWN MES\Check Sheet\Check Sheet Brkt Switch - Trial HVPT 170325.pdf# | Trial Report | [12 empty] | FALSE | C/T = 55 detik/5 pcs = 11 detik/pcs PPM = 5 SPH = 300
78 |  | 124.146 | 2025-03-12 | Trial | Kirim sample untuk Trial Harden di PT NST |  | Pak Kardi |  | NST |  | SK85M |  | 463 |  |  |  | Kirim sample ke Eudonia untuk trial nickel plating |  |  | Ersa | 2025-03-18 | 0 | Trial Hardening |  |  |  |  | IRD Harden 9.3 | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\IRD Trial Hardening - Spring Console - Tinggi 9.3mm.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\IRD Trial Hardening - Spring Console - Tinggi 9.3mm.pdf# | IRD Harden 9.5 | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\IRD Trial Hardening - Spring Console - Tinggi 9.5mm.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\IRD Trial Hardening - Spring Console - Tinggi 9.5mm.pdf# | Cp Cpk 9.3 Sesudah Harden | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sesudah Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.3mm (Sesudah Harden).xls# | Cp Cpk 9.5 Sesudah Harden | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sesudah Harden).xls#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\Cpk N30 Spring Console - Tinggi 9.5mm (Sesudah Harden).xls# | [7 empty] | FALSE | Trial Heat Treatment HV Minim (HV440-460) -> Dimensi +
79 |  | 124.146 | 2025-03-18 | Trial | Kirim sample untuk Trial Nickle Plating di PT Eudonia |  |  |  | Eudonia | - | SK85M |  | 463 |  |  |  | Sent Sample ke Customer |  |  | Ersa | 2025-03-20 | 0 | Trial Nickle Plating | [19 empty] | FALSE
81 |  | 124.146 | 2025-03-20 | Sent Sample | Sent sample ke customer |  | Pak Andri | [5 empty] | 20 | [8 empty] | 0 | Improvement | [19 empty] | FALSE | Sudah diterima Bpk. Andri 20/03/25 - 17.50 WIB
82 |  | 21-BMI05 | 2025-03-21 | Others | Sent Insp Jig |  | Pak Aji (Engineering) |  | - | - | - |  | 1 | [8 empty] | 0 | Sent Insp Jig | [19 empty] | FALSE
84 |  | 21-BMI01 | 2025-02-27 | Trial | Trial Hardening di NST untuk uji spring characteristic | [7 empty] | 1000 | Label pada tiap lot hilang saat trial harden di NST |  |  | Trial Plating di SSP |  |  | Ersa |  | 0 | Improvement | [19 empty] | FALSE | Lot M23 @500pcs & M24 @500pcs
85 |  | 21-BMI01 | 2025-03-12 | Trial | Trial Plating di SSP untuk uji spring characteristic | [7 empty] | 1000 | [8 empty] | 0 | Improvement |  |  |  |  | IRD | [14 empty] | FALSE | Lot M23 @500pcs & M24 @500pcs
86 |  | 21-BMI05 | 2025-03-21 | Sent Sample | Pengembalian Insp Jig ke MES |  | Pak Aji (Engineering) |  | - | - |  |  | 1 | [8 empty] | 0 | Sent Insp Jig | [19 empty] | FALSE
88 |  | 124.145 | 2025-04-25 | Sent Sample | Sent Last Sample |  | Pak Tanjung |  |  |  | SPS60 |  | 0 | [8 empty] | 20 | [20 empty] | FALSE
89 |  | 124.138 | 2025-04-25 | Sent Sample | Sent Last Sample |  | Pak Tanjung |  |  |  | SPS 60 |  | 0 | [8 empty] | 20 | [20 empty] | FALSE
90 |  | 124.138 | 2025-05-02 | Sent Sample | Sample untuk penawaran |  | Bu Dhea Marketing |  |  |  | SPS60 |  | 0 | [8 empty] | 5 | Kirim Sample ke MEIDOH | [19 empty] | FALSE
91 |  | 124.145 | 2025-04-29 | Trial | Trial material baru | [5 empty] | SPS60 |  | 1000 | Kelolosan untuk kontrol celah. Pada trial sebelumnya, celah sudah dapat di angka 1.2 - 1.3, tapi tidak dikontrol pada trial berikutnya (celah di angka 1.4 - 1.6). |  | Cek kestabilan celah. Jika OK, repair celah di angka 1.2 - 1.3 | Kirim sample ke NST untuk Heat Treatment | Ersa | 2025-05-02 | Ersa | 2025-05-05 | 0 | Trial |  |  |  |  | QCS | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\QCS Nut Spring (Trial Material SPS60) 290425.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\QCS Nut Spring (Trial Material SPS60) 290425.pdf# | Cp Cpk (Before Repair) | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60) Before Repair.xls#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60) Before Repair.xls# | Cp Cpk (After Repair) | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60) After Repair.xls#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60) After Repair.xls# | [9 empty] | FALSE | Hasil Cp 0.21 (NG)
92 |  | 124.138 | 2025-04-25 | Trial | Trial material baru | [5 empty] | SPS60 |  | 500 | [8 empty] | 0 | [20 empty] | FALSE
93 |  | 124.145 | 2025-05-13 | Trial | Trial celah 1,2 - 1,3 |  |  |  | F03 |  | SPS60 |  | 1000 |  |  |  | Cek N30 & Kirim sample ke NST untuk Heat Treatment |  |  | Ersa | 2025-05-14 | 0 | Improvement Celah |  |  |  |  | QCS |  | Cp Cpk | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60, Celah 1.2-1.3).pdf#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Material SPS60, Celah 1.2-1.3).pdf# | IRD Heat Treatment | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\IRD Heat Treatment - Nut Spring (90041-83025) - 170525.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\IRD Heat Treatment - Nut Spring (90041-83025) - 170525.pdf# | [9 empty] | FALSE | Celah 1,2-1,3 (Lot After Repair)
94 |  | 124.146 | 2025-05-08 | Trial | Improvement radius, tinggi diameter, celah dan tinggi | [7 empty] | 3000 | Hasil pengukuran OK dengan adanya tambahan proses press setelah forming |  |  | Kirim sample after press qty 200 pcs ke NST untuk Heat Treatment |  |  | Ersa | 2025-05-09 | 0 | Trial |  |  |  |  | QCS | \\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\QCS Spring Console Trial 080525 - Forming & Press.jpeg#\\Qc-system\project\NEW MODEL\INOVATEK\SPRING, CONSOLE DOOR STOPPER\Inspeksi\QCS Spring Console Trial 080525 - Forming & Press.jpeg# | [13 empty] | FALSE | Forming qty 2000 pcs, Forming + Press qty 1000 pcs
95 |  | 21-BMI04 | 2025-05-15 | Trial | Trial Perbaikan Durability | [7 empty] | 1 | [8 empty] | 0 | Sample untuk dikirim ke Jepang |  |  |  |  | QCS | [14 empty] | FALSE | Jika OK, buat sample qty 10 pcs untuk dikirim ke Jepang
96 |  | 124.146 | 2025-05-17 | Sent Sample | Sample Perbaikan Spring | [7 empty] | 0 | [8 empty] | 20 | [5 empty] | QCS | [14 empty] | FALSE
97 |  | 124.145 | 2025-05-21 | Trial | Untuk perubahan radius agar sama dengan inovatek ada pembuatan holder dan insert baru dan wire cut ulang camp |  |  |  | F03 |  | SPS60 |  | 2000 |  |  |  | Kirim Sample qty 1.000 pcs untuk HT di NST dan Phospating di Eudonia |  |  | Ersa | 2025-05-23 |  | Trial Perbaikan Celah |  |  |  |  | QCS |  | Cp Cpk | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Lot Holder & Insert Baru).xls#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\Cpk NUT SPRING - Cek Celah (Lot Holder & Insert Baru).xls# | IRD Heat Treatment | \\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\IRD Heat Treatment - Nut Spring (90041-83025) - 240525.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\Nut, Spring\Inspection\IRD Heat Treatment - Nut Spring (90041-83025) - 240525.pdf# | [9 empty] | FALSE | Holder dan Insert Baru
101 |  | 21-BMI03 | 2025-05-13 | Trial | Trial Internal menggunakan material yg serupa |  |  |  | P12 | 3882 | Temporary SPHC Hitam |  | 110 | [8 empty] | 0 | T0 Trial |  |  |  |  | QCS | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\T0 Trial\QCS - Spacer Trial T0 130525.pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\T0 Trial\QCS - Spacer Trial T0 130525.pdf# | Cp Cpk | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\Inspection\Cpk - -2 SPACER 230525-1 (T0 Trial).xls#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\Inspection\Cpk - #2 SPACER 230525-1 (T0 Trial).xls | Trial Report | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\T0 Trial\Trial Report - Spacer 130525.pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\T0 Trial\Trial Report - Spacer 130525.pdf# | [9 empty] | FALSE
102 |  | 21-BMI03 | 2025-05-27 | Trial | Audit kelengkapan dokumen dan Genba Check |  |  |  | P03 | 3882 | SPHC-PO |  | 1321 |  |  |  | Plating di PT Eudonia |  |  | Ersa | 2025-05-30 | 0 | Trial T1 |  |  |  |  | QCS | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\PPER\Spacer\-9 N5 - Spacer 90560-08084 (BMI).pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\PPER\Spacer\#9 N5 - Spacer 90560-08084 (BMI).pdf | Cp Cpk (After Plating) | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\PPER\Spacer\-10 N30 - Spacer 90560-08084.pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-3\PPER\Spacer\#10 N30 - Spacer 90560-08084.pdf | [11 empty] | FALSE
103 |  | 21-BMI03 | 2025-05-21 | Send Document |  |  | Pak Dicki Rahman | [5 empty] | 0 | Toleransi salah (act : +0.5, -0 , seharusnya +-0.5) sesuai standar PA |  |  | Revisi |  |  | Ersa | 2025-05-22 | 0 | [20 empty] | FALSE
104 |  | 21-BMI03 | 2025-05-27 | Send Document | Audit kelengkapan dokumen dan Genba Check |  | Pak Dicki Rahman | [5 empty] | 0 | Melengkapi dokumen yang belum (DD: 4 Juni 2025) |  |  | Follow up Approval |  |  | Selvi | 2025-05-29 | 0 | Audit Document | [19 empty] | FALSE | QCP, PIS, CF Spec dibawa langsung oleh Pak Dicki ke TBINA untuk Approval
105 |  | 123.017 | 2025-05-19 | Send Document |  |  | Pak Oman | [5 empty] | 0 | QCS belum terkirim |  |  | Kirim QCS Update |  |  | Ersa |  | 0 | Approval |  |  |  |  | QCP |  | PIS |  | Cover Document PPAP | [10 empty] | FALSE
106 |  | 21-BMI03 | 2025-06-13 | Sent Sample | Sample N30 |  | Pak Miftakhul (Purch) |  | F03 | 3882 | SPHC-PO |  | 0 | [8 empty] | 0 | Sent Sample |  |  |  |  | QCS | [14 empty] | FALSE
107 |  | 125.098 |  | Send Document | [17 empty] | 0 | [20 empty] | FALSE
108 |  | 125.098 | 2025-07-04 | Trial |  |  |  |  | P19 | 2595 | SK85M |  | 30 | Tidak mengontrol untuk pemesanan material, sehingga trial terlambat dikarenakan material belum tersedia | [7 empty] | 0 | Trial T0 |  |  |  |  | Cp Cpk | \\Qc-system\project\NEW MODEL\INOVATEK\Push On Fix\Inspection\Cp Cpk - Push On Fix - 040725.pdf#\\Qc-system\project\NEW MODEL\INOVATEK\Push On Fix\Inspection\Cp Cpk - Push On Fix - 040725.pdf# | [13 empty] | FALSE
109 |  | 125.098 | 2025-07-05 | Trial | Trial untuk sample next proses |  |  |  | P19 | 2595 |  |  | 457 |  |  |  | Kirim sample ke NST untuk proses Heat Treatment |  |  | Ersa | 2025-07-05 | 0 | Trial | [19 empty] | FALSE | Rincian qty: Cav. Cuting Depan = 219 pcs, Cav. Cuting Belakang = 238 pcs
110 |  | 125.098 | 2025-07-05 | Trial | Spec : HRC 42-50 | [7 empty] | 457 |  |  |  | Cp Cpk |  |  | Ersa | 2025-07-09 | 0 | Trial Heat Treatment |  |  |  |  | Cp Cpk | [14 empty] | FALSE | Lot Proses: HRDN/080725/1
111 |  | 125.098 | 2025-07-15 | Sent Sample | Lot Trial: 110725 |  | Pak Tanjung | [5 empty] | 0 | Part dicampur saat Heat Treatment | [7 empty] | 0 | Sent Sample |  |  |  |  | Cp Cpk | \\Qc-system\project\NEW MODEL\INOVATEK\Push On Fix\Inspection\Cp Cpk Push On Fix (Before dan After Harden) 150725.xls#\\Qc-system\project\NEW MODEL\INOVATEK\Push On Fix\Inspection\Cp Cpk Push On Fix (Before dan After Harden) 150725.xls# | QCS | [12 empty] | FALSE
112 |  | 125.118 | 2025-07-16 | Send Document |  |  | Pak Ridwan QE | [5 empty] | 0 | [8 empty] | 0 | Pengajuan Dokumen Pertama |  |  |  |  | QCP | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\PQCS\QCP - -1 Ring E (90532-08001).pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\PQCS\QCP - #1 Ring E (90532-08001).pdf | PIS | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\PQCS\PIS - -1 Ring E (90532-08001).pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\PQCS\PIS - #1 Ring E (90532-08001).pdf | CF SPEC |  | QCS | [8 empty] | FALSE
113 |  | 125.116 | 2025-07-16 | Send Document |  |  | Pak Ridwan (QE Dept) | [5 empty] | 0 | [8 empty] | 0 | Pengajuan Dokumen Pertama |  |  |  |  | QCP |  | PIS |  | CF SPEC |  | QCS | [8 empty] | FALSE
114 |  | 125.117 | 2025-07-16 | Send Document |  |  | Pak Ridwan (QE Dept) | [5 empty] | 0 | [8 empty] | 0 | Pengajuan Dokumen Pertama |  |  |  |  | QCP |  | PIS |  | CF SPEC |  | QCS | [8 empty] | FALSE
115 |  | 125.117 | 2025-07-18 | Trial | Trial BKP Pertama |  |  |  | P02 | 3197 |  |  | 10 | [8 empty] | 0 | Trial T0 |  |  |  |  | QCS | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Inspection\QCS - Washer Plate (90201-15015) - Trial T0 180725.jpeg#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Inspection\QCS - Washer Plate (90201-15015) - Trial T0 180725.jpeg# | [13 empty] | TRUE
116 |  | 125.118 | 2025-07-16 | Trial | Trial dengan material SPCC |  |  |  | P19 |  | SPCC |  | 5 | [8 empty] | 0 | Trial T0 |  |  |  |  | QCS | [14 empty] | TRUE
117 |  | 125.117 | 2025-07-24 | Trial | Trial untuk next process (plating) |  |  |  | P02 | 3197 | SPHC PO (T:3,2) |  | 642 | Setelah di-press, part tidak langsung jatuh (menempel di pad atas) |  | Menghilangkan magnet di posisi Shader dan Die Pad | Trial Plating TSH6524G-BC di Eduonia qty 200 pcs | Pak Warsono | 2025-07-25 | Ersa | 2025-07-25 | 0 | Trial T1 |  |  |  |  | Trial Report | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\Trial Report - -3 Washer Plate 90201-15015 (Trial T1 - 240725).pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\Trial Report - #3 Washer Plate 90201-15015 (Trial T1 - 240725).pdf | QCS | \\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\QCS - -3 Washer Plate 90201-15015 (Trial T1 - 240725).pdf#\\Qc-system\project\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\QCS - #3 Washer Plate 90201-15015 (Trial T1 - 240725).pdf | [11 empty] | TRUE | 1 sheet material (ukuran 1220x66) = 73 pcs
118 |  | 125.118 | 2025-08-01 | Trial | Trial menggunakan material act |  |  |  | P15 | 3091 | SK85M T:1,0 |  | 392 | Belum ada standar toleransi |  | Follow Up TBINA terkait Standar Toleransi | Trial Plating TSH6524G-BC ke Eudonia (qty 200 pcs) | Ersa | 2025-08-01 | Ersa | 2025-08-02 | 0 | Trial T1 |  |  |  |  | QCS |  | Trial Report | [12 empty] | TRUE
119 |  | 125.117 | 2025-07-31 | Sent Sample | Sample T1 Lokalisasi |  | Pak Miftakhul (Purch) |  |  |  | SPHC PO |  | 0 | [8 empty] | 30 | Sent Sample |  |  |  |  | QCS | [14 empty] | FALSE
120 |  | 125.117 | 2025-07-26 | Trial | Spec Plating : TSH6524G-BC, Prod Date : 29-Jul-25 |  | Bu Alfika |  |  |  | SPHC PO |  | 200 |  |  |  | Sent sample ke TBINA 30 pcs |  |  | Ersa | 2025-07-31 | 0 | Trial Plating |  |  |  |  | Data Insp N5 | [14 empty] | TRUE
122 |  | 125.118 | 2025-08-02 | Trial | Untuk kirim sample T1 ke TBINA |  | Miftakhul |  | Eudonia |  | SK85M T:1,0 |  | 200 |  |  |  | SST dari Eudonia Cek Cp Cpk, Kirim sample ke TBINA |  |  | Ersa | 2025-08-05 | 0 | Trial Plating TSH6524G-BC |  |  |  |  | Data Insp N5 |  | SST | [12 empty] | FALSE | 100 pcs (cav depan) & 100 pcs (cav belakang)
123 |  | 21-BMI03 | 2025-05-30 | Trial | Spec Plating : TSH6500-BC, Lot Proses: PLT/310525/1 | [5 empty] | SPHC-PO |  | 1321 | Eudonia salah spec dan warna plating. Std: TSH6500-BC (Rainbow), Act: MfZn2-K (Blue) |  | Plating ulang | Kirim part untuk plating ulang | Ersa |  | Ersa | 2025-06-10 | 0 | Trial Plating |  |  |  |  | Cp Cpk (After Plating) | [14 empty] | FALSE
124 |  | 21-BMI03 | 2025-06-10 | Trial | Spec Plating : TSH6500-BC, Lot Proses: PLT/310525/1 | [5 empty] | SPHC-PO |  | 1321 | [8 empty] | 0 | Plating ulang | [19 empty] | FALSE
125 |  | 21-BMI03 | 2025-07-30 | Trial | Trial Plating ulang (Before : TSH6500-BC, After : TSH6524-BC) -> Req TBINA |  | Pak Miftakhul | [5 empty] | 500 | [8 empty] | 0 | Plating Ulang | [19 empty] | FALSE
126 |  | 125.098 | 2025-07-15 | Sent Sample | Kirim sample ke INOVATEK |  | Pak Tanjung |  |  |  | SK85M T:0,7 |  | 0 | [8 empty] | 10 | [5 empty] | QCS |  | Surat Jalan | [12 empty] | FALSE
127 |  | 125.098 | 2025-08-02 | Sent Sample | Kirim sample ke cust INOVATEK -> PT Mah Sing Indonesia |  | Pak Tiar (Purchasing) |  |  |  | SK85M T:0,7 |  | 0 | [8 empty] | 100 | [5 empty] | QCS | [14 empty] | FALSE | Lot: PHSP/290725/1, qty 50 pcs (cav depan) & 50 pcs (cav belakang)
128 |  | 125.117 | 2025-07-31 | Sent Sample | Sample Lokalisasi |  | Pak Miftakhul (Purchasing) |  |  |  | SPHC PO T:3,2 |  | 0 |  |  |  | Follow Up untuk Feedback |  |  | Ersa | 2025-07-31 | 30 | Sent Sample T1 |  |  |  |  | QCS | [14 empty] | TRUE | Sudah diterima oleh Pak Miftakhul (konfirmasi tgl 4-Aug-25)
129 |  | 125.098 | 2025-07-11 | Trial |  |  |  |  | P19 |  |  |  | 130 | Part dicampur antara cav depan dan cav belakang |  | Memberikan tanda/spidol pada satu sisi cavity saat proses stamping | Kirim ke NST untuk Heat Treatment |  |  | Pak Udin | 2025-07-12 | 0 | Trial BKP |  |  |  |  | QCS | [14 empty] | FALSE
130 |  | 125.098 | 2025-07-12 | Trial | [8 empty] | 130 | [8 empty] | 0 | Trial Heat Treatment |  |  |  |  | Cp Cpk | [14 empty] | FALSE
131 |  | 125.098 | 2025-07-19 | Trial |  |  |  |  | P19 |  | SK85M |  | 200 |  |  |  | Kirim ke NST untuk Heat Treatment |  |  | Ersa | 2025-07-19 | 0 | Trial Perbaikan |  |  |  |  | QCS | [14 empty] | FALSE | qty 100 pcs (cav depan) & 100 pcs (cav belakang)
132 |  | 125.098 | 2025-07-19 | Trial | [8 empty] | 200 |  |  |  | Kirim ke Eudonia untuk Phospating |  |  | Ersa | 2025-07-26 | 0 | Trial Heat Treatment | [19 empty] | FALSE | Qty 100 pcs (cav depan) & 100 pcs (cav belakang), Lot Proses : HRDN/210725/1
133 |  | 125.098 | 2025-07-26 | Trial | [8 empty] | 100 |  |  |  | Kirim sample ke cust INOVATEK (PT Mah Sing Indonesia) |  |  | Ersa | 2025-08-02 | 0 | Trial Phospating | [19 empty] | TRUE | Qty 50 pcs (cav depan) & 50 pcs (cav belakang), Lot Proses : PHSP/290725/1
134 |  | 125.116 | 2025-08-09 | Trial | Trial BPK Pertama |  |  |  | P15 | 2340 | SK85M T:0,4 x 40 |  | 2 | Piercing radius kurang satu, part burry |  | Tuning | Trial T1 |  |  | Pak Ahmadi |  | 0 | Trial T0 |  |  |  |  | Data Cek N1 | [14 empty] | TRUE
135 |  | 125.138 | 2025-08-12 | Trial |  |  |  |  | P25 | 2955 | SPCC T: 1,2x173 |  | 5 | Jarak Poin 3 salah dimensi di dies (Std : 40, Act : 45) |  | Bongkar dies dan perbaikan |  | Pak Aan | 2025-08-12 |  |  | 0 | Trial T0 | [19 empty] | FALSE
136 |  | 125.072 |  | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial | [19 empty] | FALSE
137 |  | 125.072 |  | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial | [19 empty] | FALSE
138 |  | 125.072 | 2025-08-25 | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial Perbaikan | [19 empty] | FALSE
139 |  | 125.072 |  | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | Sent sample | [19 empty] | FALSE
140 |  | 125.072 |  | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | Sent sample | [19 empty] | FALSE
141 |  | 125.072 | 2025-07-31 | Sent Sample | Sample Perbaikan | [7 empty] | 0 |  |  |  | Join Check dengan MWT |  |  | Alfin | 2025-08-13 | 5 | Sent Sample | 2025-08-11 | Poin 10 (Std: 20 ±0.5 , Act: 0.76/0.70 & -0.10/-0.05) | \\Qc-system\project\NEW MODEL\MWT-AHM\Clamper trutle\Renewal Dies\SAMPLE THROTLE CABLE PT.BMI - MWT 310725.pdf#\\Qc-system\project\NEW MODEL\MWT-AHM\Clamper trutle\Renewal Dies\SAMPLE THROTLE CABLE PT.BMI - MWT 310725.pdf# | Pak Sepriadi | [15 empty] | FALSE
142 |  | 125.139 | 2025-08-13 | Trial | Sample pertama |  |  |  | P25 | 2985 | SPCC T:0,8 x 120 |  | 40 | Dimensi material yang digunakan belum sesuai (Std : 0.8 x 80, Act : 0.8 x 120), sehingga act dimensi masih ada yang terlalu panjang |  | Temporary: Shearing setelah proses | Sent sample 20 pcs ke Moreen | P' Wahyuda | 2025-08-14 | Ersa | 2025-08-15 | 0 | Trial T0 |  |  |  |  | QCS & Trial Report | \\Qc-system\project\NEW MODEL\YMI\Kawasaki 0071\Event\Hasil Trial T0 - Buffle Pipe Muffler 11 (140825).pdf#\\Qc-system\project\NEW MODEL\YMI\Kawasaki 0071\Event\Hasil Trial T0 - Buffle Pipe Muffler 11 (140825).pdf# | [13 empty] | FALSE | Program No. 43, qty OK 25 pcs & qty NG 15 pcs (NG Setting)
143 |  | 125.098 | 2025-08-02 | Trial | Phospating sisa stock harden |  |  |  | Line Phospating |  |  |  | 200 | Per tanggal 19-Aug-25, part masih belum selesai proses | [7 empty] | 0 | Trial Phospating | [19 empty] | FALSE
144 |  | 125.098 | 2025-08-18 | Trial | Join Trial & HVPT bersama PT INOVATEK & PT MAH SING |  | Pak Tanjung |  | P01 | 3128 | SK85M T:0,4 x 36 |  | 260 | Feeder error, langkah tidak stabil |  | Temporary: Setting feeder, Perbaikan maintenance |  | Pak Udin | 2025-08-19 |  |  | 0 | Trial HVPT |  |  |  |  | Trial Report & QCS |  | MoM | [12 empty] | FALSE | Req MAH SING : pengukuran di area radius, repair dies agar radius stidak maksimal
145 |  | 125.116 | 2025-08-14 | Trial | [6 empty] | SK85M T:0,4 x 40 |  | 0 | Tinggi bending minim (std 2.50 +0.7/-0 , act 1.91), visual part burry, bending rata |  | Perbaikan dies | Next Trial perbaikan |  |  | P' Ahmadi | 2025-08-27 | 0 | Trial Perbaikan | [19 empty] | TRUE | Trial perbaikan yang semula akan dilaksakan pada 27-Aug-25 diundur menjadi 29-Aug-25 dikarenakan terdapat masalah pada proses harden insert, sehingga harus dilakukan proses harden ulang (Info P' Ichsan)
146 |  | 125.098 | 2025-08-23 | Trial | Perbaikan area radius (req Mah Sing) |  |  |  | P01 | 3128 | SK85M T:0,4 x 36 |  | 200 |  |  |  | Kirim sample untuk Heat Treatment di NST |  |  | Ersa | 2025-08-25 | 0 | Trial Perbaikan Area Radius |  |  |  |  | QCS & Trial Report |  | Cp Cpk | [12 empty] | TRUE
147 |  | 125.098 | 2025-08-25 | Trial | Trial Heat Treatment untuk Lot : P1/230825/1 |  |  |  | Line Heat Treatment |  | SK85M T:0,4 x 36 |  | 200 |  |  |  | Kirim sample untuk Phospating di Eudonia |  |  | Ersa | 2025-08-29 | 0 | Trial Heat Treatment | [19 empty] | FALSE
148 |  | 125.116 | 2025-08-29 | Trial | Trial setelah perbaikan untuk supply T1 ke TBINA |  |  |  | P19 | 2970, 2980 | SK85M T:0,4 x 40 |  | 135 | Diameter luar minim (Std : 30 mm +0.7/-0, Act : 29.86 mm). Namun hasil pengukuran diameter luar sample TBINA juga minim (Act : 29.65 mm. Action : Tetap dibuatkan sample dan dilakukan proses berikutnya (heat treatment) kemudian kirim sample Supply T1 |  |  | Kirim sample untuk Heat Treatment (HV380-480) ke NST (qty 120 pcs) |  |  | Ersa | 2025-08-30 | 0 | Trial T1 |  |  |  |  | QCS & Trial Report | Z:\PROJECT\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\QCS & Trial Report - -2 Washer Plate (89978-X7A01-D) - Trial T1.pdf#Z:\PROJECT\NEW MODEL\TBINA\Lokalisasi-4\Event\Trial T1\QCS & Trial Report - #2 Washer Plate (89978-X7A01-D) - Trial T1.pdf | [13 empty] | FALSE | Trial perbaikan T1 dilakukan 2 kali yaitu pada 29 dan 30 Agustus 2025 dengan qty masing-masing 10 pcs dan 125 pcs
149 |  | 125.130 | 2025-09-12 | Sent Sample | Kirim sample T0 press part |  | Bu Meita |  | F08 |  |  |  | 0 | -Pertemuan material tajam (seharusnya dibuat radius seperti master sample) |  | Modif punch & die | -Kirim sample geomet (current process) qty 30 pcs | Pak Andi |  | Ersa | 2025-09-26 | 10 | Sample Trial T0 | 2025-09-18 |  | R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf#R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf# | Bu Meita | QCS |  | MoM 18-Sep-25 | R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf#R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf# | [11 empty] | FALSE
150 |  | 125.150 | 2025-10-08 | Trial |  |  | Pak Udin |  | P02 | 3169 |  |  | 100 |  |  | Kirim sample N30 ke CII, membandingkan data ukur berat BMI & CII | Buat ECR ke TBINA | Ersa | 2025-11-21 | Ersa | 2025-12-03 |  | Trial T0 | 2025-11-20 | Berat produk giri-giri. (Std : 4 +/-1, Act : 2,9 - 3) |  | Pak Endi Novrizal | Trial Report & QCS | [14 empty] | FALSE | OK Ratio : 100%
151 |  | 125.171 -125.174 | 2025-10-10 | Trial | Holder Exhaust Pipe 1 (JO : 1215.171) - Proses Blank |  | Pak Ari Mtc |  | P05 | 3382 | SPHC T:6,0 |  | 10 | [9 empty] | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Holder Exh Pipe (JO. 125.171).jpeg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Holder Exh Pipe (JO. 125.171).jpeg# | [13 empty] | FALSE
152 |  | 125.171 -125.174 | 2025-10-13 | Trial | Baffle Pipe Muffler 8 (JO : 125.173) - Proses : Stamping Perforating + Cutting |  | Pak Wahyuda |  | P25 | 2805 | SPCC T:1,2 |  | 35 | [8 empty] | 0 | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Perforating.jpeg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Perforating.jpeg# | [13 empty] | FALSE
153 |  | 125.171 -125.174 | 2025-10-13 | Trial | Baffle Pipe Muffler 8 (JO : 125.173) - Proses : Stamping Bending U |  | Pak Ari & Pak Ichsan |  | P03 | 3001 | SPCC T:1,2 |  | 4 | [8 empty] | 0 | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Bending U & Bending O.jpeg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Bending U & Bending O.jpeg# | [13 empty] | FALSE
154 |  | 125.171 -125.174 | 2025-10-13 | Trial | Baffle Pipe Muffler 8 (JO : 125.173) - Proses : Stamping Bending O |  | Pak Ari & Pak Ichsan |  | P03 | 3000 | SPCC T:1,2 |  | 3 | [8 empty] | 0 | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Bending U & Bending O.jpeg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Bending U & Bending O.jpeg# | [13 empty] | FALSE
155 |  | 125.171 -125.174 | 2025-10-14 | Trial | Cap End 9 (JO : 125.174) - Proses : Stamping Blank Draw |  | Pak Ichsan & Pak Ari |  | P05 | 3439 | SPCC T:1,2 |  | 2 | [8 empty] | 0 | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Cap End 9 (JO. 125.174).jpg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Cap End 9 (JO. 125.174).jpg# | [13 empty] | FALSE
156 |  | 125.171 -125.174 | 2025-10-15 | Trial | Baffle Pipe Muffler 8 (JO : 125.173) - Proses : Stamping Piercing |  | Pak Ari, Aldi |  | Komatsu OBS60 | 2420 | SPCC |  | 23 | [8 empty] | 0 | Trial T0 |  |  |  |  | Trial Report | R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Stamping Piercing.jpeg#R:\NEW MODEL\YMI\Kawasaki 3917\Event\T0\Hasil Trial T0 - Baffle Pipe Muffler 8 (JO. 125.173) - Stamping Piercing.jpeg# | [13 empty] | FALSE
157 |  | 125.151 | 2025-10-26 | Trial |  |  |  |  | Komatsu OBS 200 | 410 | SPH590-OD T:1.8 |  | 0 | Material/part akhir tidak jatuh meluncur (lengket di akhir), Wave flatness kurang nampak (Std : 0.3, Act : 0) |  | Pemasangan ejector pin, mencoba tonage up - 360 ton, penambahan support area flatness (spacer) |  | Sumino | 2025-10-27 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 100%
158 |  | 125.152 | 2025-10-26 | Trial |  |  |  |  | Komatsu OBS 200 | 4099 | SPH590-OD T:1.8 |  | 0 | Injector bending belum ditap, sedem blok belum terpasang |  | Injector ditap, sedem lok digerinding dan dipasang |  | Pak Sumino | 2025-10-26 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 100%
160 |  | 125.164 |  | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | [20 empty] | FALSE
161 |  | 125.165 | 2025-10-22 | Trial |  |  |  |  | 60T | 3593 | SK85M T:0,5 |  | 0 | Dimensi hole NG (Std : 6.9 +0/-0.15, Act : 6.1), Material belum stabil karena belum ada guide lifter pin |  | Punch piercing diperbesar, contour punch & die diimprove (turun contour), Pemasangan guide lifter |  | Pak Udin | 2025-10-23 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 75%
163 |  | 125.146 | 2025-10-24 | Trial |  |  | Pak Amin |  | Komatsu OBS 200 |  | SPH590-OD T:2.3 |  | 0 | Part mark proses bending |  | Gerinding die profile 1 (0.2) , Gerinding die profile 2 (0.2) | Trial T1 | Pak Amin | 2025-10-25 | Pak Amin | 2025-10-28 | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 73%
164 |  | 125.146 | 2025-10-28 | Trial |  |  | Pak Amin |  | Komatsu OBS200 |  | SPH590-OD T:2.3 |  | 0 | Bending masih over (poin 5 masih NG) |  | Striper insert 1 digerinding contournya 0.05 & dishim 0.15, Die bending 1 digerinding contournya 0.05, Die restrike 1 digerinding contournya 0.05 | Trial T2 (Perbaikan) | Pak Amin | 2025-11-04 | Pak Amin | 2025-11-07 | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 93%
165 |  | 125.146 | 2025-11-09 | Trial |  |  | Pak Amin |  | Komatsu OBS 200 |  | SPH590-OD T:2.3 |  | 0 | Poin 6 trimming over (0.4 - 0.38) |  | Potong die 0.2, Striper wire cut 0.2, Ganti punch trim baru | Trial T3 | Pak Amin | 2025-12-10 |  |  | 0 | Trial T2 | [19 empty] | FALSE | OK Ratio : 93%
166 |  | 125.146 | 2025-11-10 | Trial |  |  |  |  | Komatsu OBS 200 |  | SPH590-OD T:2.3 |  | 0 | [8 empty] | 0 | Trial T3 | [19 empty] | FALSE | OK Ratio : 100%
167 |  | 125.147 | 2025-10-28 | Trial |  |  | Pak Amin |  | Komatsu OBS 200 | 4103 | SPH590-OD T:2.3 |  | 0 | Hasil cutting profile ada step 0.2 mm, Pilot area punch off tidak center 1 pc |  | Cek draw, Geser pilot, sesuai draw | Trial T1 (Perbaikan) | Pak Amin | 2025-12-01 | Pak Amin | 2025-11-03 | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 73%
168 |  | 125.147 | 2025-11-03 | Trial |  |  | Pak Amin |  | Komatsu OBS 200 | 4103 | SPH590-OD T:2.3 |  | 0 | Part rawan nempel di atas setelah punch off |  | Tambah ejector di area punch off | Trial T2 | Pak Amin | 2025-11-05 | Pak Amin | 2025-11-06 | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 93%
169 |  | 125.147 | 2025-11-06 | Trial |  |  | Pak Amin |  | Komatsu OBS 200 | 4103 | SPH590-OD T:2.3 |  | 0 | Bending 90 derajat OK, setelah lanjut bending 90 derajat bukak |  | Radius di die plate |  | Pak Amin | 2025-11-08 |  |  | 0 | Trial T2 | [19 empty] | FALSE | OK Ratio : 100%
170 |  | 125.148 | 2025-10-17 | Trial |  |  | Pak Ambi |  | Komatsu OBS 200 |  | JSC590R-SD T:1.2 |  | 0 | Profile surface kurang buka/tutup |  | Setting clereance | Trial T1 | Pak Ahmadi | 2025-10-24 | Pak Ahmadi | 2025-10-25 | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 80%
171 |  | 125.148 | 2025-10-25 | Trial |  |  | Pak Ambi |  | Komatsu OBS 200 |  | JSC590R-SD T:1.2 |  | 0 | Hole datum tidak center |  | Geser hole 0.3 mm |  | Pak Ahmadi | 2025-11-05 |  |  | 0 | Trial T1 | [5 empty] | x#http://x# | [13 empty] | FALSE
172 |  | 125.149 | 2025-10-17 | Trial |  |  | Pak Ambi |  | Komatsu OBS 200 | 4102 | JSC590R-SD T:1.2 |  | 0 | Lifter belakang kepanjangan tidak bisa auto, Pembawa material putus, Produk tidak jatuh |  | Potong 5 mm, pembebas guide lifter tidak center di str, tambah tapes area part off | Trial T1 | Pak Ahmadi | 2025-10-24 | Pak Ambi | 2025-10-25 | 0 | Trial T0 | [19 empty] | FALSE | NG Ratio : 85%
173 |  | 125.149 | 2025-11-05 | Trial |  |  | Pak Ambi |  | Komatsu OBS 200 |  | JSC590R-SD T:1.2 |  | 0 | Clereance profile surface kurang buka/nutup 0.3 |  | Setting clereance bend | Trial T2 | Pak Ahmadi | 2025-11-10 | Pak Ahmadi | 2025-11-19 | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 90%
174 |  | 125.150 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 3 | Sample T0 |  |  |  | Pak Taufik | [15 empty] | FALSE
175 |  | 125.150 | 2025-11-05 | Sent Sample | Kirim sample (Lot T0) | [7 empty] | 0 | [8 empty] | 80 | Sample PO 1 |  |  |  | Pak Ikhsanudin (PT CII) | [15 empty] | FALSE | Trial T0 tidak menggunakan material sesuai drawing
176 |  | 125.150 | 2025-11-06 | Sent Sample | Lot : P1/051125/2 |  |  |  | P07 |  | SAPH440 |  | 1100 | [8 empty] | 720 | Sample PO 1 |  |  |  | Pak Ikhsanudin | [15 empty] | FALSE
177 |  | 125.150 | 2025-11-17 | Sent Sample | Lot : P1/151125/1 |  | Pak Ikhsanudin |  | P07 |  | SAPH440 |  | 0 |  |  |  | Buat PCR terkait berat produk |  |  | Ersa |  | 0 | Sample PO 1 | 2025-11-20 | Berat produk giri-giri, warna material berbeda |  | Pak Endy Novrizal | [15 empty] | FALSE
178 |  | 125.165 | 2025-11-05 | Trial |  |  |  |  | 60T | 3593 | SK85M T:0,5 |  | 0 | Dimensi hole masih NG | [7 empty] | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 75%
179 |  | 125.166 | 2025-10-21 | Trial |  |  |  |  | 60T | 3595 | S65 |  | 0 | Material belum bisa stabil saat geser karena belum terpasang guide lifter pin, Data dimensi masih NG (Std : 7.6 +0.1/-0 , Act : 7.45) |  | Pemasangan guide lifter pin, Punch blank diperkecil (cek toleransi), diameter punch diperbesar |  | Pak Udin | 2025-10-23 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 83%
180 |  | 125.166 | 2025-10-31 | Trial |  |  |  |  | 60T | 3595 | S65 |  | 200 |  |  |  | Trial Phospating di Eudonia |  |  | Ersa | 2025-10-27 | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 100%
181 |  | 125.163 | 2025-10-27 | Trial |  |  |  |  | Komatsu OBS 200 | 4077 | SPH440-OD T:2.0 |  | 0 | Blok 3 : Part lengket diproses burring, punch burring r3 insert r1, Lifter kurang naik part nyangkut di punch burring, Spring injector temporary, part nempel di atas cut off, part deform cut off, pembebas scrap kurang cut off |  | R punch dikecilin, die plate dicb 5.0, ganti spring hijau p 12 x 45, pasang injector, gr die insert, milling die plate |  | Pak Ambi | 2025-10-29 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 80%
182 |  | 125.164 | 2025-10-28 | Trial |  |  |  |  | Komatsu OBS 200 | 4087 | SPH440-OD T:2.3 |  | 0 | Blok 1 (Belum potong blank), Blok 2 (Proses bend lengket di bawah, spring injector temporary), Blok 3 (part lengket di bawah proses burring, spring temporary, jalannya punch mentok si punch burring, part melengkung/miring sesudah proses piercing) |  | Ganti spring, coba die plate lifter naik 5.0, tambah injector |  | Pak Ambi | 2025-10-29 |  |  | 0 | Trial T0 | [19 empty] | FALSE | OK Ratio : 96%
183 |  | 125.163 | 2025-11-03 | Trial |  |  |  |  | Komatsu ABS 200 | 4077 | SPH440-OD T:2.0 |  | 20 | [8 empty] | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 100%
184 |  | 125.130 | 2025-09-26 | Sent Sample |  |  | Bu Meita |  | F09 |  | SK85M T:0.8 |  | 0 | [8 empty] | 30 | Sample Proses Geomet |  | Hasil geomet OK | [17 empty] | FALSE | Sample proses geomet (current process/sebelum perbaikan)
185 |  | 125.146 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 3 | Sample T0 |  |  |  | Pak Taufik | [15 empty] | FALSE
186 |  | 125.148 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 3 | Sample T1 | [19 empty] | FALSE
187 |  | 125.149 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 3 | Sample T1 | [19 empty] | FALSE
188 |  | 125.151 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | Sample T0 | [19 empty] | FALSE
189 |  | 125.152 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SPH590-OD T:1,8 x 173 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
190 |  | 125.165 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | Sample T0 | [19 empty] | FALSE
191 |  | 125.166 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
192 |  | 125.163 | 2025-10-28 | Sent Sample | [8 empty] | 0 | [8 empty] | 0 | Sample T0 | [19 empty] | FALSE
193 |  | 125.130 | 2025-09-13 | Trial |  |  |  |  | F09 |  | SK85M |  | 215 |  |  |  | Heat Treatment di NST |  |  | Ersa | 2025-09-13 | 0 | Trial T0 | 2025-09-18 |  | R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf#R:\NEW MODEL\Trim Rubber\MoM 180925 - Hose Clamp 0.8X10X130 (8943679430).pdf# | Bu Meita | [15 empty] | FALSE
194 |  | 125.130 | 2025-09-13 | Trial |  |  |  |  | Line Heat Treatmenet |  | SK85M |  | 215 |  |  |  | Geomet Silver di Meidoh |  |  | Ersa | 2025-09-17 | 0 | Trial Heat Treatment | [19 empty] | FALSE
195 |  | 125.130 | 2025-09-17 | Trial |  |  |  |  | F09 |  | SK85M |  | 215 |  |  |  | Sent sample geomet ke customer |  |  | Ersa | 2025-11-11 | 345 | Trial Geomet Silver | [19 empty] | FALSE | Proses geomet terdapat 2 kondisi part (after harden & original forming), karna qty geomet min 300 pcs
196 |  | 125.130 | 2025-11-11 | Sent Sample |  |  | Bu Meita |  | F09 |  | SK85M T:0.8 |  | 0 |  |  | Perbaikan dies |  | Pak Ari |  |  |  | 10 | Sample After Perbaikan | 2025-12-11 | Poin 3 (sudut) dan poin 6 (diameter expanded) masih NG |  | Bu Meita | QCS | [14 empty] | FALSE
197 |  | 125.130 | 2025-09-22 | Trial | Sesuai request berdasarkan MoM 180925 |  |  |  | F08 |  | SK85M |  | 500 |  |  |  | Trial heat treatment |  |  | Ersa | 2025-09-23 | 0 | Trial Perbaikan Dies | [19 empty] | FALSE
198 |  | 125.130 | 2025-09-23 | Trial | Lot Perbaikan Dies |  |  |  | Line Heat Treatment |  | SK85M |  | 500 |  |  |  | Trial geomet silver |  |  | Ersa | 2025-10-01 | 0 | Trial Heat Treatment | [19 empty] | FALSE
199 |  | 125.130 | 2025-10-01 | Trial |  |  |  |  | Line Plating |  | SK85M T:0.8 |  | 500 | Proses tertunda karna adanya masalah pada harga penawaran |  |  | Sent sample after perbaikan ke Trim Rubber |  |  | Ersa |  | 0 | Trial Geomet Silver | [19 empty] | FALSE
200 |  | 125.130 | 2025-12-13 | Trial |  |  |  |  | F09 |  | SK85M |  | 100 | Ø Expanded di angka 15,75 (original forming) visual ngecap |  |  | Trial heat treatment di NST |  |  | Ersa | 2025-12-15 | 0 | Trial Perbaikan Ø Expanded | [19 empty] | FALSE
201 |  | 125.130 | 2025-12-15 | Trial |  |  |  |  | Line Heat Treatment |  | SK85M |  | 100 | Diameter expanded dan jarak NG (Kondisi sudah Heat Treatment) |  |  | Proses geomet silver di Meidoh |  |  | Ersa | 2025-12-19 | 0 | Trial Heat Treatment (Perbaikan 2) | [19 empty] | FALSE
202 |  | 125.150 | 2025-12-18 | Trial | Penambahan dimensi diameter untuk menambah berat part |  |  |  | P03 | 3203 |  |  | 16 |  |  |  | Konfirmasi & kirim sample ke CII |  |  | Ersa | 2025-12-19 | 0 | Trial Perbaikan Berat | 2025-12-19 | Sample terbaru by PO |  | Pak Endi Novrizal - CII | [15 empty] | FALSE
203 |  | 125.171 | 2025-10-10 | Trial | Stamping Blank |  |  |  | P05 | 3382 | SPHC T:6 |  | 10 | Timbul chip pada sisi produk (yang terakhir) |  |  |  | P' Ichsan |  |  |  | 0 | [20 empty] | FALSE
204 |  | 125.173 | 2025-10-13 | Trial | Stamping Bending U |  |  |  | P03 | 3001 | SPCC T:1,2 |  | 0 | Nylon masih kasar | [7 empty] | 0 | [20 empty] | FALSE
205 |  | 125.173 | 2025-10-13 | Trial | Stamping Bending O |  |  |  | P03 | 3000 | SPCC T:1,2 |  | 0 | Diameter minim, tetapi masih masuk toleransi (Act: 34.85 - 34.95) | [7 empty] | 0 | [20 empty] | FALSE
206 |  | 125.174 | 2025-10-14 | Trial | Stamping Blank-Draw |  |  |  | P05 | 3439 | SPCC T:1,2 |  | 0 | NG Dimensi -> Tinggi (Std : 10 mm, Act : 15.45 mm). Penyebab : Spring terlalu menekan, radius punch blank kurang beasr |  | Ganti spring (lepas spring atas, spring bawah ganti warna hijau) |  | P' Ichsan | 2025-10-15 |  |  | 0 | Trial T0 | [19 empty] | FALSE
207 |  | 125.174 | 2025-10-15 | Trial | Stamping Blank-Draw |  |  |  | P02 | 3450 | SPCC T:1.2 |  | 0 |  |  |  | Ukur R |  |  | P' Ichsan | 2025-10-16 | 0 | Trial Perbaikan | [19 empty] | FALSE | Dimensi tinggi sudah OK (Std : 10 mm, Act : 10.06 mm)
208 |  | 125.173 | 2025-10-15 | Trial | Stamping Piercing |  |  |  | Komatsu OBS60 | 2420 | SPCC T:1.2 |  | 23 | [8 empty] | 0 | [20 empty] | FALSE
209 |  | 125.171 | 2025-10-17 | Trial | Stamping Piercing |  |  |  | P05 | 3187 | SPHC-PO T:6.0 |  | 0 | Stripper tidak kuat (part menempel di atas), Hasil half kurang nongol (std : 3mm, act : 0.2mm) | [7 empty] | 0 | [20 empty] | FALSE
210 |  | 125.173 | 2025-10-30 | Trial | Tig Welding |  |  |  | Tig Welding |  | SPCC T:1.2 |  | 0 |  |  |  |  | P' Andi |  |  |  | 0 | [20 empty] | FALSE
211 |  | 125.174 | 2025-10-31 | Trial | Stamping Blank |  |  |  | P16 | Manual | SPCC T:1.2 |  | 222 | [8 empty] | 0 | [20 empty] | FALSE
212 |  | 125.162 | 2025-11-01 | Trial | Stamping Blank Forming |  |  |  | Komatsu OBW 200 | 3815,7 | SPCC T:1.6 |  | 24 | Tinggi bending minim | [7 empty] | 0 | [20 empty] | FALSE
213 |  | 125.171 | 2025-11-01 | Trial | Stamping Blank |  |  |  | P01 | 3090 | SPHC-PO T:6.0 |  | 50 | [8 empty] | 0 | [20 empty] | FALSE
214 |  | 125.171 | 2025-11-01 | Trial | Stamping Piercing (Half Punch) + Piercing 2 & Shaving |  |  |  | P01 | 3210 | SPHC-PO T:6.0 |  | 0 | [8 empty] | 0 | [20 empty] | FALSE
215 |  | 125.173 | 2025-11-07 | Trial | Stamping Bending U | [5 empty] | SPCC T:1.2 |  | 0 | Rantai mesin putus sehingga DH tidak bisa naik/turun |  | Perbaikan oleh Mtc Mesin |  | Mtc Mesin | 2025-11-07 |  |  | 0 | [20 empty] | FALSE
216 |  | 125.130 | 2025-12-24 | Trial | Perbaikan diameter expanded (ganti spare part) |  |  |  | F09 |  | SK85M |  | 100 |  |  |  | Trial Heat Treatment di PT NST |  |  | Ersa | 2025-12-24 | 0 | Trial Perbaikan 3 | [19 empty] | FALSE | Trial 2 kondisi masing-masing qty 50 pcs. Kondisi A (Sudut : 85 - 88), Kondisi B (Sudut : 78 - 80)
217 |  | 125.130 | 2025-12-24 | Trial |  |  |  |  | Line Heat Treatment |  | SK85M |  | 0 | [8 empty] | 0 | Trial Heat Treatment (Perbaikan 3) |  | Hasil pengukuran : Kondisi B OK tetapi diameter expanded dibuat OK di QCS | [17 empty] | FALSE | Trial 2 kondisi masing-masing qty 50 pcs. Kondisi A (Sudut : 85 - 88), Kondisi B (Sudut : 78 - 80)
218 |  | 125.165 | 2025-11-10 | Trial |  |  |  |  | 60T | 3593 | SK85M T:0,5 x 40 |  | 500 |  |  |  | Trial Heat Treatment di NST |  |  | Ersa | 2025-11-15 | 0 | Trial T2 | [19 empty] | FALSE | OK Ratio : 100%
220 |  | 125.164 | 2025-11-09 | Trial |  |  |  |  | Komatsu OBS200 |  | SPH440-OD T:2.3 |  | 20 | [8 empty] | 0 | Trial T1 | [19 empty] | FALSE | OK Ratio : 100%
221 |  | 125.146 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | SPH590-OD T:2,3 |  | 0 | [8 empty] | 106 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/251225
222 |  | 125.147 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SPH590-OD T: 2,3 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
223 |  | 125.147 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | SPH590-OD T: 2,3 |  | 0 | [8 empty] | 106 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/251225
224 |  | 125.148 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SPC590 T:1,2 x 78 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
225 |  | 125.148 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | SPC590 T:1,2 x 78 |  | 0 | [8 empty] | 53 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/140125/1
226 |  | 125.149 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SPC590 T:1,2 x 78 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
227 |  | 125.149 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | SPC590 T:1,2 x 78 |  | 0 | Lot pagi NG Dent | [7 empty] | 53 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/140125/2
228 |  | 125.151 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SPH590-OD T:1,8 x 173 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
229 |  | 125.151 | 2026-01-15 | Sent Sample | [6 empty] | SPH590-OD T:1,8 x 173 |  | 0 | [8 empty] | 53 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/140125/1
230 |  | 125.152 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | SPH590-OD T:1,8 x 173 |  | 0 | [8 empty] | 53 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot : P1/140125/1
231 |  | 125.165 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | SK85M T:0,5 x 40 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
232 |  | 125.165 | 2026-01-15 | Sent Sample | [6 empty] | SK85M T:0,5 x 40 |  | 0 | [8 empty] | 62 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot :
233 |  | 125.166 | 2025-10-28 | Sent Sample |  |  | Pak Taufik |  |  |  | S65 T:0,25 x 32 |  | 0 | [8 empty] | 3 | Sample T0 | [19 empty] | FALSE
234 |  | 125.166 | 2026-01-15 | Sent Sample |  |  | Pak Jiwantokoh |  |  |  | S65 T:0,25 x 32 |  | 0 | [8 empty] | 128 | PO : 25.12.190.060 (ETA TBINA) | [19 empty] | FALSE | Lot :
235 |  | 125.148 | 2025-11-19 | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial T2 | [19 empty] | FALSE | OK Ratio : 100%
236 |  | 125.165 | 2025-11-15 | Trial |  |  |  |  | Line Heat Treatment |  |  |  | 500 |  |  |  | Trial Phospating di Eudonia |  |  | Ersa | 2025-11-27 | 0 | Trial Heat Treatment | [19 empty] | FALSE
237 |  | 125.165 | 2025-11-27 | Trial |  |  |  |  | Line Phospating |  |  |  | 500 | [8 empty] | 0 | Trial Zinc Phospate Coating | [19 empty] | FALSE
238 |  | 125.166 | 2025-10-27 | Trial | [8 empty] | 200 | [8 empty] | 0 | Trial Zinc Phospate Coating | [19 empty] | FALSE
239 |  | 125.146 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [5 empty] | SPH590-OD T:2,3 |  | 66 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
240 |  | 125.147 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [5 empty] | SPH590-OD T:2.3 |  | 66 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
241 |  | 125.146 | 2025-12-19 | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial Penambahan Marking | [19 empty] | FALSE
242 |  | 125.147 | 2025-12-19 | Trial | [8 empty] | 0 | [8 empty] | 0 | Trial Penambahan Marking | [19 empty] | FALSE
243 |  | 125.147 | 2025-12-29 | Trial | Sent PO : 25.12.190.060 | [5 empty] | SPH590-OD T:2,3 |  | 189 | [8 empty] | 0 | PO : 25.12.190.060 | [19 empty] | FALSE
245 |  | 125.148 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [7 empty] | 44 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
246 |  | 125.149 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [7 empty] | 54 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
247 |  | 125.146 | 2025-12-30 | Trial | Sent PO : 25.12.190.060 | [7 empty] | 160 | [8 empty] | 106 | PO : 25.12.190.060 | [19 empty] | FALSE
248 |  | 125.148 | 2025-12-14 | Trial | Sent PO : 25.12.190.060 |  |  |  | Komatsu OBS 200 |  | SPC590 T:1,2 |  | 114 | [8 empty] | 53 | PO : 25.12.190.060 | [19 empty] | FALSE
249 |  | 125.149 | 2026-01-14 | Trial | Sent PO : 25.12.190.060 |  |  |  | Komatsu OBS 200 |  | SPC590 T:1,2 |  | 88 | Dent | [7 empty] | 53 | PO : 25.12.190.060 | [19 empty] | FALSE | Saat trial pertama, part dent qty 100 pcs. Sehingga trial kembali pada shfit 2 qty 88 pcs.
250 |  | 125.151 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [5 empty] | SPH590-OD T:1.8 |  | 72 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
251 |  | 125.151 | 2026-01-14 | Trial | Sent PO : 25.12.190.060 |  |  |  | P10 |  | SPH590-OD T:1.8 |  | 111 | [8 empty] | 53 | Sent | [19 empty] | FALSE
252 |  | 125.152 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [7 empty] | 60 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
253 |  | 125.152 | 2026-01-14 | Trial | Sent PO : 25.12.190.060 | [7 empty] | 111 | [8 empty] | 53 | PO : 25.12.190.060 | [19 empty] | FALSE
254 |  | 125.163 | 2025-11-11 | Trial | Trial untuk PO 1 dari MRP | [5 empty] | SPH440-OD |  | 130 | [8 empty] | 0 | PO | 2026-01-24 | Part tidak masuk mold di MRP |  | Pak Afif QC | [15 empty] | FALSE
255 |  | 125.164 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [7 empty] | 80 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
256 |  | 125.163 | 2025-11-27 | Trial | Trial untuk stock SPTT#2 | [5 empty] | SPH440-OD |  | 84 | [8 empty] | 0 | SPTT#2 | [19 empty] | FALSE
257 |  | 125.163 | 2026-01-28 | Trial | Request improvement dari MRP (Poin 5). Problem : Tidak masuk mold di MRP |  |  |  | P10 |  | SPH440-OD |  | 30 | Masih mekar (poin 5) |  | Improve penambahan stopper | Cek Cp Cpk | P' Ichsan | 2026-01-29 | Alfin | 2026-01-29 | 0 | Trial Perbaikan | [19 empty] | FALSE
258 |  | 125.163 | 2026-01-29 | Trial | Request improvement dari MRP (Poin 5). Problem : Tidak masuk mold di MRP |  |  |  | P10 |  | SPH440-OD |  | 30 |  |  |  | Cek Cp Cpk |  |  | Alfin |  | 0 | Trial Perbaikan | [19 empty] | FALSE | Hasilnya max 0.25, Standar Drawing 0.3 Max => Seharusnya sudah OK , tapi tinggi Flange ada yang Max >0,3 dan posisi Hole Datum 2 semua maximal
259 |  | 125.130 | 2026-02-11 | Trial | Trial sebelum Mass Pro (sudut) |  |  |  | F09 |  | SK85M T:0,8 |  | 300 |  |  |  | Trial Heat Treatment di NST |  |  | Ersa | 2026-02-12 | 300 | Trial | [19 empty] | FALSE | Setting sudut range 77-78
260 |  | 125.130 | 2026-02-12 | Trial | Trial sebelum Mass Pro (sudut) |  |  |  | Line Heat Treatment |  | SK85M T:0,8 |  | 300 |  |  |  | Trial Geomet Silver di Meidoh |  |  | Ersa |  | 300 | Trial Heat Treatment | [19 empty] | FALSE | Setting sudut range 77-78
261 |  | 125.130 | 2026-02-12 | Sent Sample | Request dari customer jepang (sample untuk ekspor) | [5 empty] | SK85M T:0,8 |  | 0 | [8 empty] | 100 | Kirim sample ke Trim Rubber | [19 empty] | FALSE
262 |  | 125.151 | 2026-02-10 | Trial | LPE |  |  |  | P10 |  | SPH590-OD T:1.8 |  | 300 | [8 empty] | 0 | LPE | [19 empty] | FALSE | Untuk sisa permintaan sample event LPE TBINA
263 |  | 125.151 | 2026-02-09 | Sent Sample | LPE | [5 empty] | SPH590-OD T:1,8 x 173 |  | 0 |  |  |  | Kirim sisa permintaan sample (82 pcs) |  |  | Ersa | 2026-02-12 | 2 | LPE | 2026-02-10 | Terdapat perubahan qty kirim sample (Sebelum : 2 pcs, sesudah : 84 pcs) |  | Pak Miftakhul / Pak Jiwantokoh | [15 empty] | FALSE | Menggunakan sisa lot sebelumnya (PO : 25.12.190.060)
264 |  | 125.152 | 2026-02-11 | Trial | LPE |  |  |  | P10 |  |  |  | 300 | [9 empty] | LPE | [19 empty] | FALSE | Untuk sisa permintaan sample event LPE TBINA
265 |  | 125.152 | 2026-02-09 | Sent Sample | LPE | [7 empty] | 0 |  |  |  | Kirim sisa permintaan sample (82 pcs) |  |  | Ersa | 2026-02-12 | 2 | LPE | 2026-02-10 | Terdapat perubahan qty kirim sample (Sebelum : 2 pcs, sesudah : 84 pcs) |  | Pak Miftakhul / Pak Jiwantokoh | [15 empty] | FALSE | Menggunakan sisa lot sebelumnya (PO : 25.12.190.060)
266 |  | 125.152 | 2026-02-12 | Sent Sample | Sisa permintaan sample LPE | [7 empty] | 0 | [8 empty] | 82 | LPE | [19 empty] | FALSE
267 |  | 125.151 | 2026-02-12 | Sent Sample | Sisa permintaan sample LPE | [7 empty] | 0 | [8 empty] | 82 | LPE | [19 empty] | FALSE
268 |  | 124.001 | 2026-04-02 | Trial | Untuk Trial Geomet di PPA |  |  |  | F01 |  | SPS60 |  | 1500 |  |  |  | Trial Geomet di PPA |  |  | P'Saudi |  | 0 | Trial | [19 empty] | FALSE
269 |  | 124.002 | 2026-04-04 | Trial | Untuk Trial Geomet di PPA |  |  |  | F01 |  | SPS60 |  | 2000 |  |  |  | Trial Geomet di PPA |  |  |  |  | 0 | Trial | [19 empty] | FALSE
270 |  | 124.003 | 2026-04-01 | Trial | Untuk Trial Geomet di PPA |  |  |  | F01 |  | SK85M |  | 1000 | Hasil geomet di PPA terkelupas (NG Visual), PPA lanjut trial ulang. |  |  | Trial Geomet di PPA |  |  |  |  | 0 | Trial | 2026-06-10 |  | MoM#http://MoM# | [16 empty] | FALSE
271 |  | 125.172 | 2026-04-30 | Trial | Proses P1 dan P2 |  |  |  | P07 |  |  |  | 0 | Proses P2, tidak bisa langsung proses Gang(Flange+Piercing + Burring) Tapi harus satu persatu: - Flane - Piercing - Burring | [7 empty] | 0 | N200 | [19 empty] | FALSE
272 |  | 125.171 | 2026-04-30 | Trial | Proses Stamping P1 Blank |  |  |  | P05 |  | SPCC T6.0 |  | 260 | [8 empty] | 0 | QAV YMI N200 | [19 empty] | FALSE
273 |  | 125.171 | 2026-04-30 | Trial | Proses Stamping P2 Piercing |  |  |  | P03 |  |  |  | 0 | Produk nempel di Striper | [7 empty] | 0 | QAV YMI N200 | [19 empty] | FALSE
274 |  | 125.173 | 2026-04-30 | Trial | Proses Perforating |  |  |  | P25 |  |  |  | 0 | -. Jarak hole perforating terhadap sisi cutting tidak simentris setelah piercing |  | Setting ulang spec jarak hole ke cutting, Buat Standar supaya setelah piercing hole simetris | [5 empty] | 0 | QAV YMI N200 | [19 empty] | FALSE
275 |  | 125.173 | 2026-04-30 | Trial | Stamping Piercing |  |  |  | P05 |  | SPCC |  | 0 | Belumm ada pokayoke pada proses |  | Penambahan pokayoke | [5 empty] | 0 | QAV N200 | [19 empty] | FALSE
277 |  | 125.173 | 2026-04-30 | Trial | Proses P2 - Piercing |  |  |  | P05 |  |  |  | 0 | [8 empty] | 0 | QAV YMI N200 |  | Request add soper pokayoke supaya produk di dies tidak terbalik, add Pin sisi kanan | [17 empty] | FALSE
278 |  | 125.173 | 2026-04-30 | Trial | P3 - Bending U | [7 empty] | 0 | [8 empty] | 0 | QAV YMI N200 |  | Request Stoper depan/belakang | [17 empty] | FALSE
279 |  | 123.016 |  | Trial | [8 empty] | 0 | [8 empty] | 0 | [20 empty] | FALSE
280 |  | 126.117 | 2026-07-31 | Trial | P1 (Blank), P2 (Piercing), P3 (Piercing 2 / Collar Assy) |  |  |  | P13 | 3930 | SPCC T:1,6 |  | 38 |  |  |  | Kirim sample non plating ke pak eksi ymi qty 5 pcs, kirim sample ke Eudonia untuk trial plating qty 20 pcs |  |  | Ersa | 2026-08-03 | 5 | Trilal T0 | 2026-08-03 | Flatness NG (oblak), Dimensi pitch antar slot berbeda-beda |  | Pak Eksi | [15 empty] | FALSE | Trial menggunakan dies temporary
281 |  | 126.117 | 2026-08-03 | Trial | Trial Plating di Eudonia | [7 empty] | 0 | [8 empty] | 20 | Trial Plating | [19 empty] | FALSE
282 |  | 126.117 | 2026-08-03 | Sent Sample | [8 empty] | 0 | [8 empty] | 5 | Sample T0 | 2026-08-03 | Flatness NG (Oblak), Dimensi pitch antar slot berbeda-beda |  | Pak Eksi YMI | [15 empty] | FALSE
283 |  | 124.001 |  | Trial | Trial Geomet di PPA |  |  |  | Line PPA |  |  |  | 0 | Hasil geomet di PPA terkelupas (NG Visual) |  | Trial ulang di PPA | Trial plating zinc black di Kosashima |  |  |  |  | 0 | Trial Geomet (Surface Treatment) | 2026-06-10 |  | MoM#http://MoM# | [16 empty] | FALSE
284 |  | 124.002 |  | Trial | Trial geomet di PPA |  |  |  | PPA Line |  |  |  | 0 | Hasil geomet di PPA terkelupas (NG Visual) |  | Trial ulang di PPA | [5 empty] | 0 | Trial Geomet (Surface Treatment) | 2026-06-10 |  | MoM#http://MoM# | [16 empty] | FALSE
285 |  | 124.003 |  | Trial | Trial Geomet di PPA |  |  |  | Line PPA |  |  |  | 0 | Hasil geomet di PPA terkelupas (NG Visual) |  | Trial ulang di PPA | [5 empty] | 0 | Trial Geomet (Surface Treatment) | [19 empty] | FALSE
286 |  | 124.001 | 2026-08-03 | Trial | Trial plating zinc black di Kosashima |  |  |  | Line Kosashima |  |  |  | 0 | [8 empty] | 30 | Trial Surface Treatment | [19 empty] | FALSE
287 |  | 124.002 | 2026-08-03 | Trial | Trial plating zinc black di Kosashima |  |  |  | Line Kosashima |  |  |  | 0 | [8 empty] | 30 | Trial Surface Treatment | [19 empty] | FALSE
288 |  | 124.003 | 2026-08-28 | Trial | Trial Geomet di PPA |  |  |  | Line ST PPA |  |  |  | 0 | [8 empty] | 100 | Trial Surface Treatment | [19 empty] | FALSE
289 |  | 126.117 | 2026-08-05 | Trial | Perbaikan sample T0 berupa penambahan stopper piercing PULSAR |  |  |  | P13 |  | SPCC T:1,6 |  | 8 | [8 empty] | 5 | Trial Perbaikan | 2026-08-10 |  |  | Pak Eksi | [15 empty] | FALSE
290 |  | 126.117 | 2026-08-10 | Trial |  |  |  |  | P06 | 3946 | SPCC T:1,6 |  | 32 |  |  |  | Kirim sample qty 30 pcs ke YMI |  |  | Ersa | 2026-08-11 | 30 | Request Sample N30 | [19 empty] | FALSE
291 |  | 126.117 | 2026-08-06 | Sent Sample | [8 empty] | 5 | [8 empty] | 5 | Sample After Perbaikan | 2026-08-10 |  |  | Pak Eksi, Pak Falah | [15 empty] | FALSE
292 |  | 126.117 | 2026-08-11 | Sent Sample | [8 empty] | 30 | [8 empty] | 30 | Request Sample N30 |  |  |  | Pak Eksi, Pak Rozy, Pak Eri | [15 empty] | FALSE
293 |  | 124.001 | 2026-08-28 | Trial | Trial Geomet Kedua di PT PPA |  |  |  | Line ST PPA |  |  |  | 0 | [8 empty] | 100 | Trial Surface Treatment | [19 empty] | FALSE
294 |  | 124.002 | 2026-08-28 | Trial | Trial Geomet Kedua di PT PPA | [7 empty] | 0 | [8 empty] | 100 | Trial Surface Treatment | [19 empty] | FALSE
295 |  | 026.002.015 | 2026-09-22 | Sent Sample | Kirim sample ke-2 Qty 4 Set (8 Pcs) | [7 empty] | 0 | Bending Masih Max => Di rework | [7 empty] | 0 | N5 |  |  |  |  | QCS (OK QC) | \\192.168.1.121\Project\NEW MODEL\MTM (Menara)\ARM\Inspection\QCS - LOWER ARM (MJPAJA-SMALA1N000-01) - 220926.pdf#\\192.168.1.121\Project\NEW MODEL\MTM (Menara)\ARM\Inspection\QCS - LOWER ARM (MJPAJA-SMALA1N000-01) - 220926.pdf# | [13 empty] | FALSE
296 |  | 026.002.016 | 2026-09-22 | Sent Sample | Kirim sample ke2 Qty 4Set (8 Pcs) | [7 empty] | 0 | Jarak bending max => Produk repair | [7 empty] | 0 | Sample N5 |  |  |  |  | Qcs | \\192.168.1.121\Project\NEW MODEL\MTM (Menara)\ARM\Inspection\QCS - UPPER ARM (MJPAJA-SMALA1N000-02) - 220926.pdf#\\192.168.1.121\Project\NEW MODEL\MTM (Menara)\ARM\Inspection\QCS - UPPER ARM (MJPAJA-SMALA1N000-02) - 220926.pdf# | [13 empty] | FALSE
297 |  | 125.162 | 2026-09-18 | Trial |  |  |  |  | P07 & P08 |  | SPCC T:1,6 |  | 200 | [8 empty] | 0 | N200 - PP Event YMI | [19 empty] | FALSE | Part OK 100%
298 |  | 125.171 -125.174 | 2026-09-21 | Trial | [6 empty] | Assy |  | 0 | 1. Body End Muffler 3 : P3 - Pie + Burr, Problem tinggi burring minim (std : 9.4 ±0.5, act : 7-8), 2. Belum ada guidance untuk positioning welding proses TW - Assy 2 + Cap End 9 (manual), berpotensi variasi panjang dan posisi welding tidak stabil. |  |  | 1. Perbaikan dengan memperkecil lubang piercing, 2. Proses fix menggunakan welding robot dengan modifikasi penambahan guide stopper |  |  | Pak Andi |  | 0 | N200 - PP Event YMI | [19 empty] | FALSE
299 |  | 125.171 -125.174 | 2026-09-25 | Sent Sample | Sample pengganti event N30 karna ada problem pada part SPI | [7 empty] | 0 | [8 empty] | 30 | Sample N30 | [19 empty] | FALSE | Lot event N200 (kondisi tinggi burring minim dan tig welding manual)