## Table___Project_List_Master
ID Project List | JO No | Project User | Date Receive | Part No | Part Name | Customer | Model | No Doc | Material Spec | Material Thickness | Material Width | Process | T0 Target | T0 Actual | Plan Start | Plan Finish | Actual Start | Actual Finish | PP1 | PP2 | MP | Remark Project list | Status Project
51 | 026.002.015 |  | 2026-02-26 | MJPAJA-SMALA1N000-01 | LOWER ARM | MTM | FLANGE-TYPE |  | SPHC270 | 1.6 | 0
53 | 026.002.016 | BMI | 2026-02-26 | MJPAJA-SMALA1N000-02 | UPPER ARM | MTM | FLANGE-TYPE |  | SPHC270 | 1.6 | 0
5 | 123.016 |  |  | 01HN-2003-13 | COVER PLATE | Velasto | [5 empty] | Stamping | [9 empty] | Alih Loading NKP
6 | 123.017 |  |  | VMVRIP-BB03900-SB | LOWER PLATE 163 X 99 | Velasto | [5 empty] | Stamping | [9 empty] | Alih Loading NKP
7 | 123.018 |  |  | VMVRIP-BB03560-CM | UPPER PLATE 123 X 87 | Velasto | [5 empty] | Stamping | [9 empty] | Alih Loading NKP
47 | 124.001 |  |  | 90466-T0054-B | CLIP, HOSE | Velasto |  |  | SPS60 | 1 | 0 | Forming
48 | 124.002 |  |  | 90466-T0019 | CLIP | Velasto |  |  | SPS60 | 1 | 12 | Forming
49 | 124.003 |  |  | 90467-16014 | CLIP | Velasto |  |  | SPS85 | 1 | 10 | Forming
8 | 124.100 | BMI | 2024-07-01 | CSM-SOCKET-P1 | SOCKET HOLDER P1 | Citra | [5 empty] | Progressive | [9 empty] | Renewal Dies Socket, Lamp Holder Besi 1 & 2 - JW
15 | 124.114 |  | 2024-12-23 | BWN-F7876-00 | BRACKET SWITCH | MES | BWN |  |  | 0 | 0 | Stamping | [9 empty] | New Dies
10 | 124.135 |  | 2024-09-01 | 18310-K18-9000-29 | PIPE TAIL MUFFLER COMP | YMI | [5 empty] | Perforating | 2024-10-03 | [8 empty] | Perforating Die for Pipe Tail 18310-K18-9000-29
11 | 124.138 |  | 2024-09-20 | 90179-06349-A | NUT | INOVATEK | [5 empty] | Forming | 2024-10-24 | [8 empty] | Tooling Nut 90179-06349
12 | 124.145 |  | 2024-09-20 | 90041-83025 | NUT, SPRING | INOVATEK | [5 empty] | Forming | 2024-10-24 | [8 empty] | Tooling Nut Spring 90041-83025
13 | 124.146 |  | 2024-09-20 | 58967-KK030-A | SPRING, CONSOLE DOOR STOPPER | INOVATEK | [5 empty] | Forming | 2024-10-24 | [8 empty] | Tooling Spring Console Door Stopper 650A 58967-KK030
14 | 124.155 |  | 2024-10-04 | 18240-K59A-A100 | PLATE HEAD GUARD | YMI | [5 empty] | Progressive | [9 empty] | Reneweal Dies Plate Heat Guard K59A AB0300060
24 | 125.072 |  |  | 17913-K59A-A100 | CLAMPER THROTTLE CABLE | MWT |  |  |  | 0 | 0 | Progressive | [9 empty] | Renewal Dies Clamper Throttle Cable
17 | 125.098 |  |  | INOVATEK-002 | PUSH ON FIX | INOVATEK |  |  | SK85M | 0 | 36 | Stamping | 2025-06-24
21 | 125.105 |  | 2025-05-13 | MB394618-TI | CLIP MB394618-TI | INGRESS |  |  | SK85 | 1 | 0 | Forming
19 | 125.116 |  | 2025-06-12 | 89978-X7A01-D | WASHER PLATE | TBINA |  |  | SK85 | 0 | 0 | Stamping Progressive | 2025-07-24 | 2025-07-16 | [7 empty] | Lokalisasi
20 | 125.117 |  | 2025-06-12 | 90201-15015 | WASHER PLATE | TBINA |  |  | SPH270C | 3 | 0 | Stamping Progressive | 2025-07-24 | 2025-07-18 | [7 empty] | Lokalisasi
18 | 125.118 |  | 2025-06-12 | 90523-08001 | RING E | TBINA |  |  | SK85 | 1 | 0 | Stamping Progressive | 2025-07-24 | [8 empty] | Lokalisasi
25 | 125.130 |  | 2025-08-18 | 8943679430 | HOSE CLAMP 0.8X10X130 | TRIM RUBBER |  |  |  | 0 | 0 | Forming
22 | 125.138 |  | 2025-07-24 | 49129-0884 | BUFFLE PIPE MUFFLER 18 | YMI | KAWASAKI 0071 |  | SPCC | 1 | 160 | Stamping Perforating | 2025-08-19 | [8 empty] | New Project
23 | 125.139 |  | 2025-07-24 | 18170-0013 | BUFFLE PIPE MUFFLER 11 | YMI | KAWASAKI 0071 |  | SPCC | 1 | 80 | Stamping Perforating | 2025-08-19 | [8 empty] | New Project
26 | 125.146 |  | 2025-08-04 | 72751-X7A02 | BRACKET, SPRING SUPPORT, RH | TBINA | 737D |  | SPH590-OD BSDG3101 | 2 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
27 | 125.147 |  | 2025-08-04 | 72751-X7A03 | BRACKET, SPRING SUPPORT, LH | TBINA | 737D |  | SPH590-OD BSDG3101 | 2 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
28 | 125.148 |  | 2025-08-04 | 71214-X7A12 | FRAME, RR SEAT CUSHION SIDE, RH | TBINA | 737D |  | SPC590 | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
29 | 125.149 |  | 2025-08-04 | 71215-X7A09 | FRAME, RR SEAT CUSHION SIDE, LH | TBINA | 737D |  | SPC590 | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
30 | 125.150 |  | 2025-08-04 | 71356-X7A09 | PLATE, RR SEAT BACK HINGE, INNER | TBINA | 737D |  | SPH440-OD | 0 | 0 | Progressive | 2025-10-20 | 2025-10-08 | [7 empty] | New Project
31 | 125.151 |  | 2025-08-04 | 71425-X7A04 | PATCH, RR SEAT LEG, RH | TBINA | 737D |  | SPH590-OD | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
32 | 125.152 |  | 2025-08-04 | 71425-X7A05 | PATCH, RR SEAT LEG, LH | TBINA | 737D |  | SPH590-OD | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
37 | 125.162 |  | 2025-08-19 | 18110-0291 | BODY END MUFFLER 7 | YMI | KAWASAKI 3917 |  | SPCC | 2 | 0 | Stamping | 2025-10-20 | [8 empty] | New Project
35 | 125.163 |  | 2025-09-08 | 71243-X7A15 | BRACKET, RR SEAT CUSHION HINGE, RH | TBINA | 737D |  | SPH440-OD | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
36 | 125.164 |  | 2025-09-08 | 71243-X7A17 | BRACKET, RR SEAT CUSHION HINGE, LH | TBINA | 737D |  | SPH440-OD | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
33 | 125.165 |  | 2025-08-20 | 79716-X1400-C | NUT | TBINA | 737D |  | SPS85 | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
34 | 125.166 |  | 2025-08-20 | 79716-X1C00-B | NUT | TBINA | 737D |  | S65 | 0 | 0 | Progressive | 2025-10-20 | [8 empty] | New Project
39 | 125.171 |  | 2025-08-19 | 18069-0605 | HOLDER EXHAUST PIPE 1 | YMI | KAWASAKI 3917 |  | SPHC-PO | 6 | 0 | Stamping Perforating, Welding | 2025-10-20 | 2025-10-10 | [7 empty] | New Project
38 | 125.171 -125.174 |  | 2025-08-19 | 18091-1377B-C02 | BODY END MUFFLER COMP | YMI | KAWASAKI 3917 |  |  | 2 | 0 | Assembly | 2025-10-20 | [8 empty] | New Project
40 | 125.172 |  | 2025-08-19 | 1811C-0290 | BODY END MUFFLER 3 | YMI | KAWASAKI 3917 |  | SPCC | 2 | 0 | Stamping | 2025-10-20 | [8 empty] | New Project
41 | 125.173 |  | 2025-08-19 | 49129-0886 | BUFFLE PIPE MUFFLER 8 | YMI | KAWASAKI 3917 |  | SPCC | 1 | 0 | Stamping | 2025-10-20 | 2025-10-13 | [7 empty] | New Project
42 | 125.174 |  | 2025-08-19 | 39031-0046 | CAP END 9 | YMI | KAWASAKI 3917 |  | SPCC | 1 | 0 | Stamping | 2025-10-20 | [8 empty] | New Project
43 | 125.191 |  | 2025-09-11 | 18310-HA26-N800-22 | Body Inner B | YMI | HA26 |  | SUS409 | 0 | 0 | Perforating, Blank
44 | 125.250 |  | 2025-12-15 | 66801 | HOSE CLAMP ASSY | SGS |  |  |  | 0 | 0
45 | 125.251 |  | 2025-12-15 | 61801 | HOSE CLAMP ASSY | SGS |  |  |  | 0 | 0
46 | 125.252 |  | 2025-12-15 | 61002 | HOSE CLAMP ASSY | SGS |  |  |  | 0 | 0
50 | 126.117 |  |  | 21007-0797A | ROTOR | YMI |  |  | SPCC | 2 | 0
1 | 21-BMI01 |  | 2021-04-01 | 14204-X1T00-G | HOOK, CLAMP | TBINA |  |  |  | 3 | 39 | Forming | [9 empty] | Lokalisasi
2 | 21-BMI02 |  |  | 90045-21188-J | RING, HOLE SNAP | Welindo | [5 empty] | Forming | [9 empty] | Lokaslisasi
3 | 21-BMI03 |  | 2025-02-04 | 90560-08084 | SPACER | TBINA |  |  | SS41 or SHP28C |  |  | Stamping Progressive | 2025-05-20 | 2025-06-13 | [7 empty] | Lokalisasi
4 | 21-BMI04 |  |  | 12-06769-A02 | ASTING TONG | FTR | [5 empty] | Stamping | [9 empty] | Lokalisasi
16 | 21-BMI05 |  | 2024-12-23 | BWN-F7335-00 | REINF., 1 | MES | BWN |  |  | 0 | 0 | Stamping